Development Plan
Version 1.0

Eclipse Process Framework

R1.0

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 6/19/2006 | 1.0 | Detailed | Chris Armstrong |

Table of Contents

Releases	2

Constraints	2

Phases	2

1	Inception – Lifecycle Objectives (LCO) Milestone	3

2	Elaboration – Lifecycle Architecture (LCA) Milestone	3

3	Construction – Initial Operational Capability (IOC) Milestone	3

4	Transition – Product Release Milestone	3

Iterations	4

Measurements	5

1	Release burndown	5

2	Iteration burndown	5

Resources	5

1	Project management	5

2	Package owner	5

3	Content development	5

4	Configuration management	5

5	Deployment	5

6	Testing	5

7	Outreach	5

Development Process	5

1	Requirements	5

2	Analysis & Design	5

3	Implementation	5

4	Configuration and Change Management	5

5	Project Management	6

6	Test	6

Comments and Questions	6

# Releases

| Release Name | Description | Start Date | End Date | # Weeks | Objectives |
| --- | --- | --- | --- | --- | --- |
| Release 1.0 | OpenUP/Basic | 23 Dec 2005 | 30 Sep 2006 | 40 | - Governance process in place, including guidelines for how to work with CVS - Tutorials available to help people adopt EPF composer - Process tools matured and usable to produce a broad set of processes and method content. - Basic set of interfaces / APIs defined, stabilized, and delivered. - Deliver basic printing capability - Mature content. Deliver at least two exemplary processes; Basic Unified Process and Agile. - Generate a high level of interest around EPF v1.0. Press releases, papers, tutorials, workshops, presentations, etc. - Identify a broader set of process champions with an interest to contribute to EPF within a specific domain, such as MDA or project management, or a specific vertical such as telecom. |
| Release 1.1 |  | 1 Oct 2006 | 31 Dec 2006 | 13 |  |
| Release 2.0 |  |  |  |  |  |

# Constraints

| Person hours (internal) |  |
| --- | --- |
| Person hours (external) |  |
| Software expense |  |
| Hardware expense |  |
| Other expenses |  |
| Total |  |

# Phases

| Phase Name | Start Date | End Date | # Days | # Iterations | Comments |
| --- | --- | --- | --- | --- | --- |
| Inception | 12/23/2005 | 1/15/2006 | 24 | 1 |  |
| Elaboration | 1/16/2006 | 4/15/2006 | 90 | 2 |  |
| Construction | 4/16/2006 | 8/31/2006 | 138 | 3 |  |
| Transition | 9/1/2006 | 9/30/2006 | 30 | 1 |  |

## Inception – Lifecycle Objectives (LCO) Milestone

### Objectives

- Objective #1

- Objective #2

### Evaluation criteria

- Evaluation criteria #1

- Evaluation criteria #2

## Elaboration – Lifecycle Architecture (LCA) Milestone

### Objectives

- Objective #1

- Objective #2

### Evaluation criteria

- Evaluation criteria #1

- Evaluation criteria #2

## Construction – Initial Operational Capability (IOC) Milestone

### Objectives

- Objective #1

- Objective #2

### Evaluation criteria

- Evaluation criteria #1

- Evaluation criteria #2

## Transition – Product Release Milestone

### Objectives

- Objective #1

- Objective #2

### Evaluation criteria

- Evaluation criteria #1

- Evaluation criteria #2

# Iterations

| # | Phase Name | Start Date | End Date | # Days | Objectives |
| --- | --- | --- | --- | --- | --- |
| M0 | Inception | 12/23/2005 | 1/15/2006 | 24 | - Project acceptance and provisioning - IBM donation - Project environment established - Committer meeting - Project organization and plan agreed to |
| M1 | Elaboration | 1/16/2006 | 2/28/2006 | 44 | - Legal process to be completed by initial committers - Train all committers. - Provision project, set up website, mailing lists, etc. - Agree on structure of OpenUP/Basic, agree on how to structure of OpenUP/Basic into work units, principles and resources to evolve each unit. - Define structural work units for the Agile process - Define XML schema - Understand required changes to donated code and meta-model - Publish proposed set of APIs - Identify outreach activities |
| M2 | Elaboration | 3/1/2006 | 4/15/2006 | 46 | - Naming convention agreed to - Freeze structural information for OpenUP/Basic (e.g. all guidelines, work products, etc. defined) - End-to-end agile process defined with outlined content. - Engage with additional contributors - Agree on user experience and have a few examples for agile content and OpenUP/Basic - Validate extensibility / composibility of OpenUP/Basic - Freeze feature request on tooling / meta model - Freeze XML schema - Freeze APIs |
| M3 | Construction | 4/16/2006 | 6/1/2006 | 47 | - Produce documentation (online help, tutorials, etc.) - Identify an initial set of key promoters presenting at conferences, writing blogs and articles, etc. Well-defined plan for v1.0 launch. - Freeze structure of OpenUP/Basic and Agile/XP |
| M4 | Construction | 6/2/2006 | 7/15/2006 | 44 |  |
| M5 | Construction | 7/16/2006 | 8/31/2006 | 47 | - G11N and accessibility validation - Finalize launch plan - Improve documentation (online help, tutorials, etc.) - Code and content freeze |
| M6 | Transition | 9/1/2006 | 9/30/2006 | 30 | - End game - Produce launch collateral - Plan next release |

# Measurements

## Release burndown

## Iteration burndown

# Resources

<insert organization chart>

## Project management

## Package owner

## Content development

## Configuration management

## Deployment

## Testing

## Outreach

# Development Process

## Requirements

Use OpenUP/Basic without use cases; individual process elements comprise most detailed functional requirements

## Analysis & Design

Use EPF plug-in development process

## Implementation

Use EPF plug-in development process

## Configuration and Change Management

Use OpenUP/Basic extended for distributed development

## Project Management

Use OpenUP/Basic extended for distributed development

## Test

Use OpenUP/Basic replacing process content review and process piloting for testing techniques

# Comments and Questions

- Comment #1

- Comment #2