## Items
Item # | Type | Description | Status | Priority | Points | Iteration | Notes | Assigned to | Effort (hours) | I0 | Week 1 | Week 2 | Week 3 | Week 4 | I1 | Week 1 | Week 2 | Week 3 | Week 4 | I2 | Week 1 | Week 2 | Week 3 | Week 4 | I3 | Week 1 | Week 2 | Week 3 | Week 4 | I4 | Week 1 | Week 2 | Week 3 | Week 4 | I5 | Week 1 | Week 2 | Week 3 | Week 4
1 | Use Case | Prepare Event Billing | Assigned |  | 10
2 | Use Case | Register for Event | Decomposed
2.1 | Use Case | Basic Flow (without email) | Assigned |  | 2 | 1
2.2 | Use Case | Basic Flow (with email) | Assigned |  | 2 | 2
2.3 | Use Case | Event full | Assigned |  | 1 | 2
2.4 | Use Case | Invalid registration | Assigned |  | 5 |  |  | Jim
2.4.1 | Task | UI for simple case | Assigned |  |  | 1 |  | Jim | 12 | 3
2.4.2 | Task | Business logic for simple case | Assigned |  |  | 1 |  | Joe | 14 | 4
2.4.3 | Task | Add to "3 strikes and u are out" | Assigned |  | 1 | 2 |  | Per
2.4.4 | Task | Add recover password | Assigned |  | 1 | 3 |  | Jim
2.5 | Use Case | Email system unavailable | Assigned |  | 1 | 3
2.6 | Use Case | Cancel registration | Assigned |  | 1 | 3
2.7 | Use Case | Change registration | Assigned |  | 1 | 4
2.8 | Use Case | Register for multiple events | Assigned |  | 1 | 4
2.9 | Use Case | Request driving directions | Assigned |  | 2 | 5
3 | Use Case | Add to wait list | Assigned |  | 3 | 5
3.1 | Use Case | Attendee already registered | Assigned |  | 1 | 6
3 | Use Case | Confirm Event Registration | Assigned |  |  | 2
4 | Use Case | Order Event Materials | Assigned |  |  | 4
5 | Use Case | Manage Events | Assigned |  |  | 3
6 | Use Case | Manage Instructors | Assigned |  |  | 5
7 | Use Case | Market Events | Assigned |  |  | 5
8 | Use Case | View Instructor Profile | Assigned |  |  | 6
9 | Use Case | View Event Profile | Assigned |  |  | 6
10 | Use Case | Close Event Delivery | New |  |  | 6
10 | Supporting Requirement | Performance Requirements
10 | Supporting Requirement | Usability Requirements
10 | Supporting Requirement | Reliability Requirements
Total |  |  |  |  | 32

## I1 Tasks
|  |  |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7
|  |  |  | 6/2-6/3 |  | 6/4-6/10 |  | 6/11-6/23 |  | 6/18-6/24 |  | 6/25-7/1 |  | 7/2-7/14 |  | 7/9-7/15
Item # | Item Summary | Description | Assigned To | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual
2.1 | Basic Flow (without email) | Detail use case | Chris
2.1 | Basic Flow (without email) | Review use caes | Bob, Chris
2.1 | Basic Flow (without email) | Create use case realization | Sally
2.1 | Basic Flow (without email) | Design use case | Sally
2.1 | Basic Flow (without email) | Implement | Mike
2.1 | Basic Flow (without email) | Test | John
2.1 | Basic Flow (without email) | Evaluate | John
2.2 | Basic Flow (with email) | Implement, test, and evaluate | Mike, Bob
n/a | Process task | Create work item list | Mary
n/a | Process task | Create I1 task list | Mary
n/a | Process task | Prepare weekly status report | Mary
n/a | Process task | Participate in weekly status meeting | Mary

## Lists
ItemTypeList
Change Request
Defect
Supporting Requirement
Task
Use Case
ItemStatusList
New
Assigned | (not to a person, but an iteration)
Completed
Accepted
Rejected
Decomposed
Priority
High
Medium
Low