## All Work Items
ID | Summary | Priority | Size Estimate (Points) | Status | TargetM | Assigned To | Effort Estimate Left (Hours) | Comments
145775 | RM - Artifact Use Case Story Board to be considered for OpenUP | P3 |  | RESO | 1.0.0 | Ana
| Decide if Use Case Story Board will be part of 1.0.0 | P3 | 1 | ASSI | 1.0 M4 | Team | 2 | Low priority enhancement.
159570 | RM - Vision Template Missing 'Priority' and 'Planned Release' Attributes for 'Other Product Requirements' | P3 |  | ASSI | 1.0.0
160093 | RM - Feedback provided | P3 |  | ASSI | 1.0.0 | Chris Sibbald |  | Address other items first as this will cover some of these comments.
160237 | RM - Move Content on Structuring the UC Model to Separate... | P3 |  | RESO | 1.0.0 | Chris Sibbald | 0 | Addressed as part of other bugs. Marked as duplicate.
167851 | RM - Determine approach for Supporting Requirements | P1 | 1 | ASSI | 1.0 M3 | Team | 2 | Need decision ASAP. Propose a vote on approach.
162628 | RM - Improve description of Role: Analyst | P3 |  | ASSI | 1.0.0
167434 | RM - Update skills for Analyst | P3 | 1 | RESO | 1.0 M3 | Chris Sibbald | 0 | Ready to Verify
167435 | General - Create Guideline: Self-Organizing Teams | P2 | 2 | ASSI | 1.0 M4 | Scott Ambler | 4 | Scott to confirm estimates of effort.
162634 | RM - Tasks need better alignment to OpenUP/Basic discipli... | P3 |  | ASSI | 1.0.0 |  | 12
167279 | RM - Update Task: Define Vision in accordance with review... | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167480 | RM - Update Task: Find and Outline Requirements | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167481 | RM - Update Task: Detail Requirements | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
162636 | RM - Concepts need better alignment to OpenUP/Basic disci... | P3 |  | ASSI | 1.0.0 |  | 18
167848 | RM - Update Concept: Requirements | P3 | 1 | ASSI | 1.0 M3 | Chris Sibbald | 2
167849 | RM - Update Concept: Use Case | P2 | 4 | ASSI | 1.0 M4 | Chris Sibbald | 8
167852 | RM - Update Concept: Use-Case Model | P2 | 2 | ASSI | 1.0 M4 | Chris Sibbald | 4
167853 | RM - Update Concept: Requirements Attributes | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
167855 | RM - Update Concept: Traceability | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
162637 | RM - Guidelines need better alignment to OpenUP/Basic dis... | P3 |  | ASSI | 1.0.0 |  | 26
167857 | RM - Update Guideline: Find and Outline Actors and Use Cases | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
167859 | RM - Update Guideline: Detail Use Cases and Scenarios | P3 | 4 | ASSI | 1.0.0 | Chris Sibbald | 8
167860 | RM - Update Guideline: Detail Use Cases and Scenarios | P3 | 0 | RESO | 1.0.0 | Chris Sibbald | 0 | Duplicate bug
167862 | RM - Complete review of Guideline: Effective Requirement ... | P2 | 1 | ASSI | 1.0 M4 | Team | 2 | Need decision on this.
167863 | RM - Update Guideline: Requirements Gathering Techniques | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167880 | RM - Update Guideline: Requirements Pitfalls | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
167887 | RM - Update Guideline: Use Case Formats | P2 | 3 | ASSI | 1.0 M4 | Chris Sibbald | 6
167888 | RM - Update Guideline: Use-Case Model | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
162638 | RM - Checklists need better alignment to OpenUP/Basic dis... | P3 |  | ASSI | 1.0.0 |  | 10
167909 | RM - Update Checklist: Vision | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
167911 | RM - Update Checklist: Qualities of Good Requirements | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
167913 | RM - Update Checklist: Use-Case Model | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
167915 | RM - Update Checklist: Use Case | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
167917 | RM - Add RM checklists to the reference guidance elements... | P3 | 1 | ASSI | 1.0 M3 | Chris Sibbald | 2
162639 | RM - Artifacts need better alignment to OpenUP/Basic disc... | P3 |  | ASSI | 1.0.0 |  | 14
167270 | RM - Update Artifact: Vision in accordance with review | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167281 | RM - Remove Artifact:Actor in accordance with review deci... | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167283 | RM - Update display name of Artifact: Use-Case Model | P3 | 1 | RESO | 1.0.0 | Chris Sibbald | 0
167439 | RM - Create Concept: Actor | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167477 | RM - Update Artifact:Glossary | P3 | 1 | ASSI | 1.0.0 | Chris Sibbald | 2
162641 | RM - Templates need better alignment to OpenUP/Basic disc... | P3 |  | ASSI | 1.0.0 |  | 6
167919 | RM - Update Template: Vision | P3 | 2 | ASSI | 1.0.0 | Chris Sibbald | 4
167924 | RM - Update Template: Use-Case Specification | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
168275 | RM - Simplify explanation and implementation of use cases | P1 | 1 | NEW | 1.0 M3 | Team | 2 | This will impact other items (167849, 167859, 167887, 167915, 167924). Need decision ASAP.
| Totals for M3 |  | 5 |  |  |  | 8
| Totals for M4 |  | 17 |  |  |  | 34
Assumptions: 1 point ~ 2 hrs ideal work.

## M3 Work Items
ID | Summary | Priority | Size Estimate (Points) | Status | TargetM | Assigned To | Effort Estimate Left (Hours) | Comments
167851 | RM - Determine approach for Supporting Requirements | P1 | 1 | ASSI | 1.0 M3 | Team | 2 | Need decision ASAP. Propose a vote on approach.
167434 | RM - Update skills for Analyst | P3 | 1 | RESO | 1.0 M3 | Chris Sibbald | 0 | Ready to Verify
168275 | RM - Simplify explanation and implementation of use cases | P1 | 1 | NEW | 1.0 M3 | Team | 2 | This will impact other items (167849, 167859, 167887, 167915, 167924). Need decision ASAP.
167848 | RM - Update Concept: Requirements | P3 | 1 | ASSI | 1.0 M3 | Chris Sibbald | 2
167917 | RM - Add RM checklists to the reference guidance elements... | P3 | 1 | ASSI | 1.0 M3 | Chris Sibbald | 2

## M4 Work Items
ID | Summary | Priority | Size Estimate (Points) | Status | TargetM | Assigned To | Effort Estimate Left (Hours) | Comments
| Decide if Use Case Story Board will be part of 1.0.0 | P3 | 1 | ASSI | 1.0 M4 | Team | 2 | Low priority enhancement.
167435 | General - Create Guideline: Self-Organizing Teams | P2 | 2 | ASSI | 1.0 M4 | Scott Ambler | 4 | Scott to confirm estimates of effort.
167849 | RM - Update Concept: Use Case | P2 | 4 | ASSI | 1.0 M4 | Chris Sibbald | 8
167852 | RM - Update Concept: Use-Case Model | P2 | 2 | ASSI | 1.0 M4 | Chris Sibbald | 4
167862 | RM - Complete review of Guideline: Effective Requirement ... | P2 | 1 | ASSI | 1.0 M4 | Team | 2 | Need decision on this.
167887 | RM - Update Guideline: Use Case Formats | P2 | 3 | ASSI | 1.0 M4 | Chris Sibbald | 6
167888 | RM - Update Guideline: Use-Case Model | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
167913 | RM - Update Checklist: Use-Case Model | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
167915 | RM - Update Checklist: Use Case | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
167924 | RM - Update Template: Use-Case Specification | P2 | 1 | ASSI | 1.0 M4 | Chris Sibbald | 2
| Totals |  | 17 |  |  |  | 34