## Sheet1
This worksheet provides the status of the RM content package as of May 26th.
Status Legend:
| proposed | Not in current library, but may be a good idea
| included | Element included in library but not complete
| draft complete | Content exists but requires review
| reviewed | Review completed and comments available for action
| finalized | Review comments incorporated and final content (and relationships) accepted.
Items in red have never received widespread review and should be the focus of the next review.
Method Element | Type | Comment | Status | Related Bugzilla Entry
Requirements | MethodPackage |  | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134915
Requirement Attributes | Concept | Complete. At the April 20th RM review there was a proposal to delete this concept. See minutes associated with bugzill entry. I feel this is a key concept for RM and should be retained. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Requirements | Concept | Complete (TBC). This concept should also be linked to Task:Define Vision and Task:Detail Requirements. See associate bug (enhancement). This has been implemented in bup_rm_plugin V0.4. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143741 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Supporting Requirements | Concept | Ana provided concept and I incorporated it in bup_rm_plugin V0.4 This has not been included in May 26 build of OpenUP/Basic. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Traceability | Concept | Complete. At the April 20th RM review there was a proposal to delete this concept. See minutes associated with bugzill entry. I feel this is a key concept for RM and should be retained. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Use Case | Concept | Added content in bup_rm_plugin V0.4 based on RUP content. Linked to Guideline:Find and Outline Actors and Use Cases, Guideline: Detail Use Cases and Scenarios, Task:Detail Requirements, Task:Find and Outline Requirements, and Artifact:Use Case | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140865 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Use Case Model | Concept | Need concept (TBC). Proposal to refactor to make use case model optional. | proposed
Actor | Checklist | Checklist exists. Needs content. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140867
Qualities of Good Requirements | Checklist | Complete Checklist now associated with Artifacts Use Case, Vision and Supporting Requirements. Associations to Tasks: Find and Outline Requirements and Detail Requirements Removed. This was done in bup_rm_plugin V0.4. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=141624 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Supporting Requirements | Checklist | Checklist Qualities of Good Requirements is associated with Artifact:Supporting Requirements in bup_rm_plugin V0.4 A checklist of the types of supporting requirements that should be considered, perhaps based on work of Peter Eeles (link attached to 140073). | proposed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073
Use Case Model | Checklist | Needs Content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140856
Use Case | Checklist | Content provided in bup_rm_plugin V0.4. (worked with Paul Bramble). | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140858 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Vision | Checklist | Checklist exists, need content. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140859
Achieving Concurrence | Guideline | Added this guideline to the guidance for Task: Find and Outline Requirements and Task: Detail Requirements in bup_rm_plugin V0.4. Guideline still needs to be re-written. See minutes of April 20 RM review attached to bugzilla 135941. Focus on requirement reviews only vs. general reviews. Re-use TwoTierReview from Paul? Should there be two guidelines: Review Use Cases, and Review Supporting Requirements? | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=140847 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Define Vision | Guideline | Should there be a guildeline for the Task:Define Vision similar to those for the other tasks? Or is Guideline: Requirements Gathering, Guideline:Achieve Concurrence and Checklist:Vision sufficient? | proposed
Detail Use Cases and Scenarios | Guideline | Content available based on work with Paul Bramble. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Find and Outline Actors and Use Cases | Guideline | Complete based on work with Paul Bramble. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=140848
Requirement Gathering Techniques | Guideline | Complete | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Requirement Pitfalls | Guideline | Complete | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Supporting Requirements | Guideline | Guideline exist (name and description only), is it needed or is Guideline:Writing Good Requirements, Checklist:Supporting Requirements and Concept:Supporting Requirements sufficient? | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073
Use Case Formats | Guideline | Not included in May 26th build of OpenUP/Basic. Guidance on formality and format of use cases. Associate with Task:Detail Requirements and Template: Use Case Specification. May require update to Template:Use Case Specification. Added Guideline in bup_rm_plugin V0.4 including draft content from Paul. Referenced this guideline from Representation Options of Artifact: Use Case. Linked to Concept:Use Case. Need to Link to Template:Use Case Specification, Artifact: Use Case and Task:Detail Requirements. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140850 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Use Case Model | Guideline | Need Content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140852
Use Case | Guideline | No longer in OpenUP (05/05/06). Replaced with Concept Use Case. Not sure if this is correct, perhaps guideline is the appropriate element. | removed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Writing Good Requirements | Guideline | Complete. Links to Task:Find and Outline Requirements and Task:Detail Requirements not in May 26th build. Bug 144235 raised. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=144235
Requirement | Term Definition | Complete. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Define Vision | Task | Substantially complete. Added step related to Glossary in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140840 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Detail Requirements | Task | Substantially complete. Added step related to Glossary in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140844 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Find and Outline Requirements | Task | Added step related to Glossary in bup_rm_plugin V0.4 WIL added as an output. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140846 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
ActorGoal List | Artifact | If we make UC Model optional there should be an artifact that captures Actors. | proposed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140871
Glossary | Artifact | updated in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134895 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Supporting Requirements | Artifact | Incorporated in bup_rm_plugin v0.4. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Use Case Model | Artifact | Exists. Proposal to make this optional and factor out into another package. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
Use Case | Artifact | Complete | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
Actor | Artifact | Exists, but only captured in UC Model. If we make UC Model optional we will need an Actor list. This WP does not show up as the input or output of any task because only the Use-Case model is an input or output. If we wish to make UC Model optional we will have to update OpenUP to list UC as input/output as appropriate. | draft completed
Vision | Artifact | needs content | included
Analyst | Role | Complete | draft completed