## Releases
Release | Start | Length | End
1.0 | 2005-12-23 | 40.2857 | 2006-09-30
2.0 | 2006-10-01 | 13.1429 | 2006-12-31
Formulas:
End = [Length]*7+[Start]-1

## R1.0 Phases
Phase | Start Date | Duration | Days | End Date | Iterations | Comments | Days Left | Ratio | Days/Iter
Inception | 2005-12-23 | 3.4286 | 24 | 2006-01-15 | 1 |  | 258 | 8.511% | 24
Elaboration | 2006-01-16 | 12.8571 | 90 | 2006-04-15 | 2 |  | 168 | 31.91% | 45
Construction | 2006-04-16 | 19.7143 | 138 | 2006-08-31 | 3 |  | 30 | 48.94% | 46
Transition | 2006-09-01 | 4.2857 | 30 | 2006-09-30 | 1 |  | 0 | 10.64% | 30
Total |  | 40.2857 | 282 |  | 7 |  |  | 100% | 40.2857
Formulas:
Start Date = [End Date, row above]+1
End Date = [Duration]*7+[Start Date]-1

## R1.0 Iterations
Iteration | Phase | Start Date | Length | End Date | Requirements | Risk | Comments | Days Left
0 | Inception | 2005-12-23 | 24 | 2006-01-15 |  |  |  | 0
1 | Elaboration | 2006-01-16 | 44 | 2006-02-28 |  |  |  | 46
2 | Elaboration | 2006-03-01 | 46 | 2006-04-15 |  |  |  | 0
3 | Construction | 2006-04-16 | 47 | 2006-06-01 |  |  |  | 91
4 | Construction | 2006-06-02 | 44 | 2006-07-15 |  |  |  | 47
5 | Construction | 2006-07-16 | 47 | 2006-08-31 |  |  |  | 0
6 | Transition | 2006-09-01 | 30 | 2006-09-30 |  |  |  | 0
|  |  | 121 | Days
|  |  | 17.2857 | Weeks
Formulas:
Start Date = [End Date, row above]+1
End Date = [Start Date]+[Length]-1

## R1.0 Resources
Discipline/role | Req FTE | Ratio | Calc FTE | Ratio | Diff FTE | Chris | Mick | Megan | Sharon | Mike M | Marj | John R | Carrie | John E | Craig | Bobbi | Mike R | Dave | Joe | Mike P
Requirements | 0.3 | 24.19% | 0.4 | 28.57% | 0.1 | 0.14 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0.02 | 0.01 | 0.02
Requirements architect | 0.05 | 4.032% | 0.05 | 3.571% | 0 | 0.05
Requirements author | 0.05 | 4.032% | 0.05 | 3.571% | 0 | 0.05
Requirements reviewer | 0.1 | 12.1% | 0.15 | 0.7143% | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Domain expert | 0.1 | 12.1% | 0.15 | 2.143% | 0.05 | 0.03 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 |  | 0.01
Analysis, Design, Arch | 0.4 | 32.26% | 0.54 | 38.57% | 0.14 | 0.31 | 0.01 | 0.01 | 0.08 | 0.03 | 0.03 | 0.03 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0 | 0 | 0
Process architect | 0.05 | 4.032% | 0.05 | 3.571% | 0 | 0.05
Process analyst | 0.1 | 8.065% | 0.2 | 7.143% | 0.1 | 0.1 |  |  | 0.04 | 0.02 | 0.02 | 0.02
Process designer | 0.15 | 12.1% | 0.18 | 10.71% | 0.03 | 0.15 |  |  | 0.03
Design reviewer | 0.1 | 8.065% | 0.11 | 7.143% | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Development, Test | 0.32 | 25.81% | 0.23 | 16.43% | -0.09 | 0.08 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0
Process author | 0.25 | 20.16% | 0.11 | 7.857% | -0.14 | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Process reviewer | 0.05 | 4.032% | 0.1 | 7.143% | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Tool specialist | 0.02 | 1.613% | 0.02 | 1.429% | 0 | 0.02
Project management | 0.22 | 17.74% | 0.23 | 16.43% | 0.01 | 0.15 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02
Process manager | 0.15 | 12.1% | 0.15 | 10.71% | 0 | 0.15
Project reviewer | 0.05 | 4.032% | 0.06 | 4.286% | 0.01 |  |  |  | 0.01 | [6 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Sponsor | 0.02 | 1.613% | 0.02 | 1.429% | 0 | [13 empty] | 0.01 | 0.01
Total FTE | 1.24 |  | 1.4 |  | 0.16 | 0.68 | 0.05 | 0.05 | 0.13 | 0.07 | 0.07 | 0.07 | 0.04 | 0.04 | 0.04 | 0.04 | 0.02 | 0.03 | 0.03 | 0.04
Percent of total effort | [5 empty] | 48.57% | 3.571% | 3.571% | 9.286% | 5% | 5% | 5% | 2.857% | 2.857% | 2.857% | 2.857% | 1.429% | 2.143% | 2.143% | 2.857%
Domain expertise
RUP | [5 empty] | X |  | X | [7 empty] | X |  | X |  | X
Data modeling | [5 empty] | X |  |  | X |  | X
Pilot project architect | [6 empty] | X |  | X |  |  |  |  | X | X
Pilot project analyst | [7 empty] | X
Pilot project designer | [7 empty] | X | [5 empty] | X | X
OOA | [5 empty] | X |  | X | [7 empty] | X |  |  |  | X
OOD | [5 empty] | X | X | X | X |  |  |  |  | X | X |  |  |  |  | X
Architecture | [5 empty] | X | X | X | X | X |  |  |  | X | X | X |  |  |  | X
XDE | [5 empty] | X | X | X | X |  |  |  |  | X | X | X |  |  |  | X
Process modeling | [5 empty] | X |  |  | X | [6 empty] | X
Coaching | [5 empty] | X | [9 empty] | X
Legacy platform | [9 empty] | X |  | X
Existing SDLC | [11 empty] | X | [7 empty] | X
Thrivent environment | [6 empty] | X |  | X | X | X | X | X |  |  | X | X | X | X | X
Testing | [5 empty] | X | [6 empty] | X
Estimate
Hours/day | 8 |  | 11.2 |  |  | 5.44 | 0.4 | 0.4 | 1.04 | 0.56 | 0.56 | 0.56 | 0.32 | 0.32 | 0.32 | 0.32 | 0.16 | 0.24 | 0.24 | 0.32
Hours/week | 40 |  | 56 |  |  | 27.2 | 2 | 2 | 5.2 | 2.8 | 2.8 | 2.8 | 1.6 | 1.6 | 1.6 | 1.6 | 0.8 | 1.2 | 1.2 | 1.6
Begin date | 2004-09-20 | 2004-10-20
End date | 2004-12-31 | 2004-12-31
Number of weeks | 14.5714 | 10.2857
Total hours remainig | 816 | 576

## Change Log
Date | Who | What
2004-10-10 | Chris | Changed phase names…
2004-10-10 | Chris | Changed iteration structure in phase plan
2004-10-10 | Chris | Release 1 finished by 12/15/04 (to allow for completion of construction by 11/30)
2004-10-24 | Chris | Changed I3 and subsequent iteration dates
2004-10-24 | Chris | Switched I4 from elaboration to construction
2004-10-24 | Chris | Switched I2 from elaboration to inception