## Burndown
Project | 4th Iteration |  |  |  |  | 5th Iteration |  |  | 6th Iteration |  |  |  | 7th Iteration
Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
Total remaining bugs | 36 | 34 | 27 | 25 | 88 | 25 | 23 | 50 | 23 | 17 | 0 | 79 | 0 | 0 | 0 | #REF! | 0
Total reminaing points | 56 | 52 | 49.5 | 49 | 62 | 74 | 74 | 25 | 34 | 92 | 75 | 75 | #REF! | #REF! | #REF! | #REF!
Burnt points this week | 9 | 9.5 | 12 | 12 | 6 | 16.5 | 14.5 | 0 | 76 | 76 | 76 | 76 | #REF! | #REF! | #REF! | #REF!
Total burnt points | 9 | 18.5 | 30.5 | 42.5 | 48.5 | 65 | 79.5 | 79.5 | 155.5 | 231.5 | 307.5 | 383.5 | #REF! | #REF! | #REF! | #REF!
Discipline | Plan |  | Actual |  |  | Plan | Actual |  | Plan |  | Actual
Requirements | 38 |  | 53 |  |  | 7 | 6 |  | 30 |  | -1
Architecture | 9 |  | 1.5 |  |  | 7 | 6 |  | 4 |  | 4
Development | 6 |  | 10 |  |  | 25 | 11.5 |  | 24 |  | 0
Test | 0 |  | 10 |  |  | 7 | 3.5 |  | 8 |  | 0
Change Mangement | 5 |  | 5 |  |  | 7 | 0 |  | 0 |  | 0
Project Management | 0 |  | 0 |  |  | 0 | 0 |  | 75 |  | 0
General | 0 |  | 0 |  |  | 7 | 0 |  | 68 |  | 0

## Method Statistics
| Total | Role | Task | Work Product | Guidance
Requirements | 61 | 1 | 6 | 10 | 44
Architecture | 17 | 1 | 3 | 2 | 11
Development | 32 | 2 | 7 | 8 | 15
Test | 19 | 1 | 4 | 4 | 10
CM | 4 | 0 | 1 | 0 | 3
PM | 48 | 1 | 6 | 5 | 36
General | 14 | 1 | 0 | 0 | 13
Total | 195 | 7 | 27 | 29 | 132

## Requirements
| Committer: | Chris Sibbald, Telelogic |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-04 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
134895 | Artifact | Glossary | 1 | 5, 6 | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
134895 | Template | Glossary | 1 | 5, 6 | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
134915 | MethodPackage | Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Artifact | Use Case Model | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Term Definition | Requirement | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Writing Good Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Use Case | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Supporting Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Requirement Pitfalls | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Requirement Gathering Techniques | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Find and Outline Actors and Use Cases | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Detail Use Cases and Scenarios | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Guideline | Achieving Concurrence | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Checklist | Qualities of Good Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Concept | Traceability | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Concept | Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
135941 | Concept | Requirement Attributes | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
140073 | Artifact | Supporting Requirements | 3 | 5, 7 | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140073 | Template | Supporting Requirements | 3 | 5, 7 | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED
140073 | Guideline | Supporting Requirements | 3 | 5, 7 | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140073 | Checklist | Supporting Requirements | 3 | 5, 7 | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140073 | Concept | Supporting Requirements | 3 | 5, 7 | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140840 | Task | Define Vision | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
140844 | Task | Detail Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
140846 | Task | Find and Outline Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
140847 | Guideline | Effective Requirements Reviews | 2 | 5, 7 | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
140848 | Guideline | Find and Outline Actors and Use Cases | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
140850 | Guideline | Use Case Formats | 2 | 6, 7 | NEW | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
140852 | Guideline | Use Case Model | 2 | 6 | NEW | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140856 | Checklist | Use Case Model | 2 | 6 | NEW | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140858 | Checklist | Use Case | 2 | 6, 7 | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
140859 | Checklist | Vision | 2 | 6, 7 | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
140865 | Concept | Use Case | 2 | 6 | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
140867 | Checklist | Actor | 2 | 6, 7 | NEW | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
140871 | Artifact | ActorGoal List | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
141624 | Checklist | Qualities of Good Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143741 | Concept | Requirements | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Task | Find and Outline Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Task | Detail Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Task | Define Vision | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Artifact | Glossary | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Artifact | Use Case | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Artifact | Supporting Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Template | Supporting Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Template | Glossary | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Guideline | Use Case Formats | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Guideline | Achieving Concurrence | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Checklist | Use Case | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Checklist | Qualities of Good Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Concept | Use Case | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Concept | Supporting Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
143764 | Concept | Requirements | 1 | 4 | RESOLVED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
144235 | Guideline | Writing Good Requirements | 2 | 6, 7 | CLOSED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | CLOSED
145773 | Guideline | Detail Use Cases and Scenarios | 2 | 6, 7 | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
145775 | Artifact | Use Case Storyboard | 1 | 5 | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | RESOLVED | RESOLVED | RESOLVED
147349 | Concept | Use Case Model | 0.66667 | 5 | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
147349 | Checklist | Use Case Model | 0.66667 | 5 | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
147349 | Guideline | Use Case Model | 0.66667 | 5 | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
147351 | Concept | Use Case Model | 2 | 6, 7 | ASSIGNED | ASSIGNED | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED
147354 | Artifact | Vision | 2 | 6, 7 | NEW | NEW | NEW | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
147356 | Role | Analyst | 1 | 5 | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | CLOSED | CLOSED | CLOSED
147431 | Artifact | Actor | 2 | 5, 7 | NEW | ASSIGNED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | RESOLVED | VERIFIED
147974 | CapabilityPattern | Manage Requirements | 4 | 5, 6 | 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED; 2006-08-04: ASSIGNED; 2006-08-09: ASSIGNED; 2006-08-16: ASSIGNED
149241 | Discipline | Requirements | 2 | 5, 6 | 2006-07-05: ASSIGNED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED; 2006-08-04: RESOLVED; 2006-08-09: RESOLVED; 2006-08-16: RESOLVED
|  | Total Points | 90 |  | 43 | 47 | 33 | 25 | 21 | 21 | 21 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 8 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 15 | 21 | 12 | 8 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 16 | 2 | 11 | 17 | 19 | 19 | 19 | 23 | 24 | 24 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 23 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 23 | 24 | 15 | 10 | 8 | 8 | 8 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 16 | 17 | 14 | 14 | 13 | 13 | 13 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 38; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 30; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted points/ week |  |  | 32.5 | 39 | 46 | 51 | 53 | 53 | 53 | 59 | 60.5 | 60.5 | 61.5
|  | Burnt Points / Week (adjusted) |  |  | 32.5 | 6.5 | 7 | 5 | 2 | 0 | 0 | 6 | 1.5 | 0 | -1
|  | Iteration Burndown |  |  | 5.5 | -1 | -8 | -13 | -15 | 7 | 7 | 1 | -0.5 | 30 | 31 | 31 | 31 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 53; 2006-07-26: Iteration Burndown:; 2006-08-02: 6; 2006-08-23: Iteration Burndown:; 2006-08-30: -1; 2006-09-20: Iteration Burndown:; 2006-09-27: 0

## Architecture
| Committer: | Mark Dickson, Xansa |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
143180 | Role | Architect | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143181 | Task | Define Architecture | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143182 | Task | Refine Architecture | 2 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143183 | Task | Demonstrate Architecture | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143185 | Work Product | Architecture | 1 | 4 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143184 | Work Product | Architectural Proof-of-Concept | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143187 | Concept | Component | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: Verified; 2006-08-16: Verified
143191 | Guideline | Create Architectural Proof-of-Concept | 1 | 6 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143192 | Guideline | Layering | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Verified; 2006-08-16: Verified
143189 | Concept | Patterns | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143186 | Guideline | Analysis Mechanisms | 1 | 4 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143188 | Guideline | Design and Implementation Mechanisms | 1 | 4 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143193 | Guideline | Representing Interfaces to External Systems | 1 | 6 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: Verified; 2006-08-16: Verified
143178 | Guideline | Visual Modeling | 1 | 5 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Verified; 2006-08-16: Verified
143179 | Guideline | Using Visualizations | 1 | 6 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: Closed; 2006-08-16: Closed
143195 | Principle | Using Patterns | 1 | 5 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
143194 | Principle | Abstracting Away Complexity | 1 | 5 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Closed; 2006-08-16: Closed
143190 | Checklist | Architecture | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
147970 | Capability Pattern | Define Architecture | 1 | 5 | 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
147971 | Capability Pattern | Determine Architectural Feasibility | 1 | 5 | 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Resolved; 2006-08-09: Verified; 2006-08-16: Verified
150761 | Discipline | Overview |  |  | 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Verified; 2006-08-16: Verified
153570 | Guideline | Demonstrate Architecture | 1 | 5 | 2006-08-09: Verified; 2006-08-16: Verified
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 2 | 2 | 6 | 5 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 7 | 7 | 12 | 13 | 12 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 3 | 10 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 9 | 9 | 18 | 18 | 18 | 11 | 11 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 10 | 10 | 19 | 19 | 19.5 | 15.5 | 15.5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 9; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 4; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted Points / week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 1.5; 2006-07-19: 5.5; 2006-07-26: 5.5; 2006-08-02: 7.5; 2006-08-09: 11.5; 2006-08-16: 11.5
|  | Burnt Points / Week (adjusted) |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 1.5; 2006-07-19: 4; 2006-07-26: 0; 2006-08-02: 2; 2006-08-09: 4; 2006-08-16: 0
|  | Iteration Burndown |  |  | 9 | 9 | 9 | 9 | 7.5 | 3.5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 1.5; 2006-07-26: Iteration Burndown:; 2006-08-02: 6; 2006-08-23: Iteration Burndown:; 2006-08-30: 4; 2006-09-20: Iteration Burndown:; 2006-09-27: 0
Note on K11: Mark Dickson: Jim Ruehlin
Note on K12: Mark Dickson: Chris Doyle
Note on K13: Mark Dickson: Chris Doyle Content submitted for review
Note on K17: Mark Dickson: Jim Ruehlin
Note on K19: Mark Dickson: Chris Doyle Content submitted for review
Note on K21: Mark Dickson: Chris Doyle
Note on N21: Mark Dickson: 26/07 Content submitted for review by Chris Doyle
Note on N22: Mark Dickson: Will be completed by 29/07 by Mark Dickson
Note on N23: Mark Dickson: Will be completed by 29/07 by Mark Dickson
Note on O18: Mark Dickson: Removed this element as it duplicates "visual_modeling"
Note on O20: Mark Dickson: descoped

## Development
| Committer: | Brian G. Lyons, Number Six Software, Inc. |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
145171 | Role | Developer | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Resolved; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
146946 | Role | Developer (vm) | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147148 | Task | Design the Solution | 2 | 4 | 2006-06-14: New; 2006-06-20: Assigned; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Reopened; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147152 | Task | Design the Solution (vm) | 1 |  | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned
147161 | Task | Implement Developer Tests | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Assigned
147141 | Task | Implement Solution | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147171 | Task | Integrate and Create Build | 2 |  | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New
147166 | Task | Prototype the User Interface | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147162 | Task | Run Developer Tests | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147149 | Work Product | Design | 1 | 4 | 2006-06-14: New; 2006-06-20: Assigned; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147153 | Work Product | Design (vm) | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147172 | Work Product | Build | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147163 | Work Product | Developer Test | 2 | 4 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147144 | Work Product | Implementation | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147154 | Work Product | Design Component | 2 |  | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New
147155 | Work Product | Use-Case Realization | 2 |  | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New
147167 | Work Product | UI Prototype | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147176 | Concept | Refactoring | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: Assigned
147165 | Concept | Test First Design | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Resolved
147177 | Concept | Continuous Integration | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: Assigned
147151 | Checklist | Design | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
150638 | Checklist | Design (vm) | 2 | 6 | 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147150 | Guideline | Design | 3 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147178 | Guideline | Continuous Integration | 2 |  | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New
147147 | Guideline | Implementation | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147173 | Guideline | Promoting Builds | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147174 | Guideline | Refactoring | 2 |  | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New
147169 | Guideline | User-Interface Prototype | 3 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147164 | Guideline | Developer Test | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147157 | Guideline | Design Components Representation | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147158 | Guideline | Use-Case Realizations | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
147156 | Concept | Entity Control Boundary Pattern | 3 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147973 | Capability Pattern | Develop Solution | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
149238 | Discipline | Overview | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
|  | Total Points | 60 |  | 56 | 55 | 49 | 46 | 47 | 49 | 41 | 41 | 41 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 30 | 28 | 24 | 15 | 17 | 16 | 17 | 17 | 17 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 1 | 2 | 3 | 10 | 9 | 10 | 6 | 6 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 1 | 4 | 7 | 8 | 7 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 31 | 30 | 27 | 25 | 26 | 27 | 23 | 23 | 23 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 56 | 55 | 52.5 | 52 | 53.5 | 27 | 23 | 23 | 23 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 6; 2006-07-26: Iteration 5 Target:; 2006-08-02: 25; 2006-08-23: Iteration 6 Target:; 2006-08-30: 24; 2006-09-20: Iteration 7 Target:; 2006-09-27: 0
|  | Unadjusted Points/week |  |  | 2006-06-14: 0; 2006-06-20: 0.5; 2006-06-28: 3.5; 2006-07-05: 6; 2006-07-12: 6.5; 2006-07-19: 5.5; 2006-07-26: 9.5; 2006-08-02: 9.5; 2006-08-09: 9.5; 2006-08-16: 9.5
|  | Burnt Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0.5; 2006-06-28: 3; 2006-07-05: 3; 2006-07-12: 3.5; 2006-07-19: 2; 2006-07-26: 7.5; 2006-08-02: 2; 2006-08-09: 0; 2006-08-16: 0
|  | Iteration Burndown |  |  | 6 | 5.5 | 2.5 | -0.5 | -4 | 23 | 15.5 | 13.5 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 10; 2006-07-26: Iteration Burndown:; 2006-08-02: 11.5; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0
Points per Iteration
[11 empty] | Iteration | Points
[11 empty] | 4 | 6
[11 empty] | 5 | 25
[11 empty] | 6 | 18

## Test
| Committer: | Brian G. Lyons, Number Six Software |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
146501 | Role | Tester | 1 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147182 | Task | Create Test Case | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
146937 | Task | Evaluate Test Results | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147183 | Task | Implement Tests | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
146940 | Task | Run Tests | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147184 | Work Product | Test Case | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147185 | Work Product | Test Data | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
146938 | Work Product | Test Log | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
146941 | Work Product | Test Script | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147194 | Concept | Test Ideas | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147188 | Concept | Types of Test | 3 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147195 | Checklist | Test Script | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147186 | Checklist | Test Case | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147187 | Checklist | Test Data | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147189 | Guideline | Failure Analysis and Report Creation | 2 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147196 | Guideline | Maintaining Automated Test Suite | 2 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147198 | Guideline | Programming Automated Tests | 2 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
147191 | Guideline | Test Ideas | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
147193 | Guideline | Test Suite | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved; 2006-08-09: Resolved; 2006-08-16: Resolved
| Capability Pattern | Test | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
| Discipline | Overview | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
|  | Total | 37 | [5 empty] | 17 | 17 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 0 | 0 | 0 | 0 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 19 | 19 | 19 | 19 | 7 | 7 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 10 | 10 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 19 | 19 | 19 | 19 | 11 | 11 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 35 | 35 | 35 | 35 | 27 | 27 | 23.5 | 23.5 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 0; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 8; 2006-09-20: Iteration 7 Target:; 2006-09-27: 0
|  | Unadjusted Points / week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 10; 2006-07-19: 10; 2006-07-26: 13.5; 2006-08-02: 13.5; 2006-08-09: 13.5; 2006-08-16: 13.5
|  | Burnt Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 10; 2006-07-19: 0; 2006-07-26: 3.5; 2006-08-02: 0; 2006-08-09: 0; 2006-08-16: 0
|  | Iteration Burndown |  |  | 0 | 0 | 0 | 0 | -10 | 7 | 3.5 | 3.5 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 10; 2006-07-26: Iteration Burndown:; 2006-08-02: 3.5; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0
Points by Iteration
[11 empty] | Iteration | Points
[11 empty] | 5 | 9
[11 empty] | 6 | 8

## Change_Management
| Committer: | Chris Sibbald, Telelogic |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-04 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
134898 | MethodPackage | Change Management | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
136341 | Task | Request Change | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
136341 | Concept | Workspace | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
136341 | Guideline | Change Requests | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
136341 | Concept | Change Requests | 1 | 4 | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED | CLOSED
147975 | CapabilityPattern | On-going Tasks | 3 | 5,6,7 | 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED; 2006-08-04: ASSIGNED; 2006-08-09: ASSIGNED; 2006-08-16: ASSIGNED
149236 | Discipline | Change Management | 3 | 5,6,7 | 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED; 2006-08-04: RESOLVED; 2006-08-09: RESOLVED; 2006-08-16: RESOLVED
|  | Total Points | 11 |  | 0 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 0 | 3 | 3 | 6 | 1900-01-05 | 1900-01-05 | 1900-01-05 | 1900-01-05 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 5; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 0; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted Points / Week |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6.5 | 6.5 | 6.5
|  | Burnt Points / Week |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
|  | Iteration Burndown |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.5 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 5; 2006-07-26: Iteration Burndown:; 2006-08-02: 0; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0

## Project_Management
| Committer: | Chris Armstrong, APG | [6 empty] | Status
Bug | Item Type | Name | Assigned | Points | Release | Iteration | Priority | Comments | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
147965 | Capability Pattern | PM - Capability Pattern assess_and_close_out_project - create content | remove | 0 | 0.9 | 6 | Low |  |  | New | New | New | New | New | New | New | Resolved | Resolved
147967 | Capability Pattern | PM - Capability Pattern assess_and_plan_iteration - create content | Per | 2 | 0.9 | 6 | High |  |  | New | New | New | New | New | New | New | Assigned | Assigned
147968 | Capability Pattern | PM - Capability Pattern initiate_project - create content | Joe | 2 | 0.9 | 6 | High |  |  | New | New | New | New | New | New | New | Assigned | Assigned
147969 | Capability Pattern | PM - Capability Pattern manage_iteration - create content | Per | 2 | 0.9 | 6 | High |  |  | New | New | New | New | New | New | New | Assigned | Assigned
146426 | Checklist | PM - Add new Checklist: Project Plan | Joe | 2 | 1.0 |  | Medium |  | New | New | New | New | New | New | New | New | Assigned | Assigned
151831 | Checklist | PM - Checklist: Iteration Plan - create | Per | 2 | 1.0 |  | Medium | [7 empty] | New | New | Assigned | Assigned
151834 | Checklist | PM - Checklist: Risk List - create | Ricardo | 2 | 1.0 |  | Low | [7 empty] | New | New | Assigned | Assigned
151832 | Checklist | PM - Checklist: Status Assessment - create | Chris | 2 | 1.0 |  | Low | [7 empty] | New | New | Assigned | Assigned
151835 | Checklist | PM - Checklist: Work Item List - create | Per | 2 | 1.0 |  | Medium | [7 empty] | New | New | Assigned | Assigned
146439 | Concept | PM - Add new Concept: Project Team | Bernie | 3 | 1.0 |  | Low |  | New | New | New | New | New | New | New | New | New | New
146476 | Concept | PM - Concept: Building Effective Teams - add content | Bernie | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146436 | Concept | PM - Concept: Iteration - update content | Per | 2 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
151827 | Concept | PM - Concept: Metrics - update content |  | 2 | 0.9 | 6 | Low | [7 empty] | New | New | New | New
146437 | Concept | PM - Concept: Milestones - Add content |  | 2 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146438 | Concept | PM - Concept: Phase - Update content | Bernie | 2 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146441 | Concept | PM - Concept: Risk - extend content | Ricardo | 1 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146440 | Concept | PM - Concept: Risk - update content | Ricardo | 1 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146482 | Concept | PM - Concept: Risk Management- update content | Ricardo | 1 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
149235 | Discipline | PM - No project management discipline text. | Chris | 1 | 0.9 | 6 | High |  |  |  |  | New | New | New | New | New | New | New
146445 | Example | PM - Add new Example: Iteration Plan | Per | 2 | 1.0 |  | Medium |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146444 | Example | PM - Add new Example: Project Plan | Joe | 2 | 1.0 |  | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146446 | Example | PM - Add new Example: Work Items List | Per | 2 | 1.0 |  | High |  | New | New | New | New | New | New | New | New | Assigned | Assigned
135397 | Guideline | PM - Add Content: Guideline: Work Item List | Per | 3 | 0.9 | 6 | High |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146468 | Guideline | PM - Add new Guideline: Use Case Points Estimation Technique |  | 3 | 1.0 |  | Low |  | New | New | New | New | New | New | New | New | New | New
146500 | Guideline | PM - Add new Reference: Anchoring the Software Process | Ricardo | 1 | 0.9 | 6 | Medium |  | New | New | New | New | New | New | New | New | New | New
151828 | Guideline | PM - Guideline: Assign Changes to an Iteration | remove guideline | 1 | 0.9 | 6 | Low | Merge w/Concept & Guideline | [6 empty] | New | New | New | New
146453 | Guideline | PM - Guideline: Assign Work - add content |  | 3 | 1.0 |  | Low |  | New | New | New | New | New | New | New | New | New | New
146454 | Guideline | PM - Guideline: Estimation - update content |  | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146455 | Guideline | PM - Guideline: Iteration Planning - update content | Per | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146456 | Guideline | PM - Guideline: Plan Project Phases - add content | Joe | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146457 | Guideline | PM - Guideline: Prioritizing Work - add content |  | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146459 | Guideline | PM - Guideline: Project Plan - add content | Ricardo | 3 | 0.9 | 4 | Low |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
146460 | Guideline | PM - Guideline: Risk List - update content | Ricardo | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146461 | Guideline | PM - Guideline: Staffing Project - add content |  | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146463 | Guideline | PM - Guideline: Status Assessment - update content | Chris | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | Assigned | Assigned
146464 | Guideline | PM - Guideline: Time-Boxed Iterations - add content | remove guideline | 1 | 0.9 | 6 | Low | Merge w/Concept & Guideline | New | New | New | New | New | New | New | New | New | New
146466 | Guideline | PM - Guideline: Type and Frequency of Assessments - add content |  | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146467 | Guideline | PM - Guideline: Types of Metrics - add content |  | 3 | 0.9 | 6 | Low |  | New | New | New | New | New | New | New | New | New | New
146477 | Practice | PM - Practice: Iterative Development - remove |  | 1 | 0.9 | 4 | Low |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
151830 | Report | PM - Report: Iteration Burndown | Per | 3 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
151829 | Report | PM - Report: Project Burndown | Joe | 3 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
151424 | Role | Project Manager | Joe | 1 | 0.9 | 6 | High | [7 empty] | Assigned | Assigned | Assigned | Assigned
151782 | Task | Assess Results | Chris | 2 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
151783 | Task | Close Out Project | remove | 0 | 0.9 | 6 | High | [7 empty] | New | New | Resolved | Resolved
151784 | Task | Initiate Iteration | remove | 0 | 0.9 | 6 | High | [7 empty] | New | New | Resolved | Resolved
151785 | Task | Plan Iteration | Per | 2 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
151426 | Task | Plan the Project | Joe | 2 | 0.9 | 6 | High | [7 empty] | Assigned | Assigned | Assigned | Assigned
146502 | Task | PM - Task: Monitor and Control Project - update content | Per | 2 | 0.9 | 6 | High |  | New | New | New | New | New | New | New | New | Assigned | Assigned
151824 | Template | PM - Template: Iteration Plan - replace | Per | 2 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
146504 | Template | PM - Template: Project Plan - replace | Joe | 2 | 0.9 | 6 | High |  | New | New | New | New | New | New | Assigned | Assigned | Assigned | Assigned
151826 | Template | PM - Template: Risk List | Ricardo | 2 | 0.9 | 6 | Medium | [7 empty] | New | New | Assigned | Assigned
151837 | Template | PM - Template: Status Assessment - create | Chris | 2 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
151836 | Template | PM - Template: Work Items List - create | Per | 3 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
151820 | Work Product | Iteration Plan | Per | 2 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
146503 | Work Product | PM - Add new Work Product: Risk List | Ricardo | 2 | 0.9 | 6 | High |  | New | New | New | New | New | New | New | New | Assigned | Assigned
151423 | Work Product | Project Plan | Joe | 2 | 0.9 | 6 | High | [7 empty] | Assigned | Assigned | Assigned | Assigned
151821 | Work Product | Status Assessment | Chris | 2 | 0.9 | 6 | High | [7 empty] | New | New | Assigned | Assigned
137120 | Work Product | Work Items List | Per | 3 | 0.9 | 6 | High |  | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned
|  | Unconfirmed | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | [6 empty] | 29 | 33 | 33 | 34 | 34 | 34 | 51 | 51 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | [6 empty] | 30 | 34 | 34 | 35 | 35 | 35 | 56 | 56 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points | [6 empty] | 60 | 60 | 60 | 61 | 61 | 61 | 90 | 56 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration | [6 empty] | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 1; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 75; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted Points / week | [6 empty] | 2006-06-14: 4; 2006-06-20: 4; 2006-06-28: 4; 2006-07-05: 4; 2006-07-12: 4; 2006-07-19: 4; 2006-07-26: 4; 2006-08-02: 4; 2006-08-09: 4; 2006-08-16: 4
|  | Burnt Points / Week | [6 empty] | 2006-06-14: 4; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0; 2006-08-09: 0; 2006-08-16: 0
|  | Iteration Burndown | [6 empty] | -3 | -3 | -3 | -3 | -3 | 7 | 7 | 7 | 75 | 75 | 75 | 75 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration | [6 empty] | 2006-07-05: Iteration Burndown:; 2006-07-12: 4; 2006-07-26: Iteration Burndown:; 2006-08-02: 0; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0

## General
|  | Committer: | Steve Adolph, UBC | Points | Iteration | Status
| Bug | Item Type | Name |  |  | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
| 133269 | Concept | Stakeholder | 4 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
| 138784 | Concept | General - Need content for Focus principle | 4 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
| 140019 |  | General - Navigation Map | 8 | 5 | 2006-06-14: Re-openned; 2006-06-20: Re-openned; 2006-06-28: Re-openned; 2006-07-05: Re-openned; 2006-07-12: Re-openned; 2006-07-19: Re-openned; 2006-07-26: Re-openned; 2006-08-02: Re-opened; 2006-08-09: Re-opened; 2006-08-16: Re-opened
| 145669 | Guideline | General - Improve Guidelines for Referencing Tasks | 8 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
| 145670 | Guideline | General - Improve Guidelines for Writing Guidances in Plu... | 4 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
| 145671 | Guideline | General - Indicate UML Prefered Diagramming Language in P... | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
| 146449 |  | General - Guidance: Copyright | 4 | 5 | 2006-06-14: Re-openned; 2006-06-20: Re-openned; 2006-06-28: Re-openned; 2006-07-05: Re-openned; 2006-07-12: Re-openned; 2006-07-19: Re-openned; 2006-07-26: Re-openned; 2006-08-02: Re-opened; 2006-08-09: Re-opened; 2006-08-16: Re-opened
| 146487 | Supporting Material | General - Glossary - seems a little light | 12 | 7 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: new; 2006-07-26: new; 2006-08-02: new; 2006-08-09: New; 2006-08-16: New
| 146489 | Supporting Material | General - Index seems light | 12 | 7 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 146491 |  | General - Graphic banner - replace | 4 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 146493 |  | General - About dialog box - inconsistent text | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 146494 |  | General - index/content.htm - title tag | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 146499 |  | General - Create OpenUP graphics | 4 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 147135 | Supporting Material | General - OpenUP White papers explaining core concepts ar... | 80 | 7 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: ASSIGNEDASSIGNED; 2006-08-02: Assigned; 2006-08-09: Assigned; 2006-08-16: Assigned
| 150766 | Role | General - Review Any Role usage. | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 150767 | Supporting Material | General - Create Getting Started Supporting Material | 25 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 150768 | Supporting Material | General - Create Overivew | 25 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 150769 | Supporting Material | General - Review and update references | 5 | 7 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 150770 | Phase Iteration Template | General - Review phase iteration templates | 5 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 150771 | Work Product Kind | General - Policy for Work Product Kind must be established | 5 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW; 2006-08-09: New; 2006-08-16: New
| 152354 |  | Re-architecting and Re-positioning OpenUP |  |  | 2006-07-26: New; 2006-08-02: New; 2006-08-09: New; 2006-08-16: New
Where do these belong???
|  | Guideline | Conduct Review/Concurrence
|  | Concept | Prototype
|  | Capability Pattern | Assess and Close Out Project
|  | Capability Pattern | Assess and Plan Iteration
|  | Capability Pattern | Initiate Project
|  | Capability Pattern | Manage Iteration
|  |  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | New |  |  | 2006-06-14: 15; 2006-06-20: 15; 2006-06-28: 14; 2006-07-05: 12; 2006-07-12: 17; 2006-07-19: 17; 2006-07-26: 17; 2006-08-02: 18
|  |  | Assigned |  |  | 2006-06-14: 7; 2006-06-20: 7; 2006-06-28: 7; 2006-07-05: 7; 2006-07-12: 6; 2006-07-19: 7; 2006-07-26: 7; 2006-08-02: 7
|  |  | Reopened |  |  | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Resolved |  |  | 3 | 3 | 7 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  |  | Remaining Bugs (New + Assigned + Reopened) |  |  | 22 | 22 | 21 | 20 | 25 | 25 | 24 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Remaining Points |  |  | 154 | 154 | 154 | 154 | 154 | 74 | 74 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 0; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 68; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  |  | Unadjusted Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0; 2006-08-09: 0; 2006-08-16: 0
|  |  | Burnt Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0; 2006-08-09: 0; 2006-08-16: 0
|  |  | Iteration Burndown |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 68 | 68 | 68 | #REF! | #REF! | #REF! | #REF!
|  |  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 0; 2006-07-26: Iteration Burndown:; 2006-08-02: 0; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0