## Burndown
Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
Actual | 84 | 85 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned | 161 | 168 | 126 | 105 | 84 | 63 | 42 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Required |  | 85 | 73 | 64.8889 | 56.7778 | 48.6667 | 40.5556 | 32.4444 | 24.3333 | 16.2222 | 8.1111 | 0

## Method Statistics
| Total | Role | Task | Work Product | Guidance
Requirements | 61 | 1 | 6 | 10 | 44
Architecture | 10 | 1 | 3 | 2 | 4
Development | 31 | 2 | 7 | 8 | 14
Test | 19 | 1 | 4 | 4 | 10
CM | 4 | 0 | 1 | 0 | 3
PM | 29 | 1 | 6 | 4 | 18
General | 8 | 1 | 0 | 0 | 7
Total | 162 | 7 | 27 | 28 | 100

## Requirements
| Committer: | Chris Sibbald, Telelogic | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
134895 | Artifact | Glossary | ASSIGNED | ASSIGNED | ASSIGNED
134895 | Template | Glossary | ASSIGNED | ASSIGNED | ASSIGNED
134915 | MethodPackage | Requirements | CLOSED | CLOSED | CLOSED
135941 | Artifact | Use Case Model | CLOSED | CLOSED | CLOSED
135941 | Term Definition | Requirement | CLOSED | CLOSED | CLOSED
135941 | Guideline | Writing Good Requirements | CLOSED | CLOSED | CLOSED
135941 | Guideline | Use Case | CLOSED | CLOSED | CLOSED
135941 | Guideline | Supporting Requirements | CLOSED | CLOSED | CLOSED
135941 | Guideline | Requirement Pitfalls | CLOSED | CLOSED | CLOSED
135941 | Guideline | Requirement Gathering Techniques | CLOSED | CLOSED | CLOSED
135941 | Guideline | Find and Outline Actors and Use Cases | CLOSED | CLOSED | CLOSED
135941 | Guideline | Detail Use Cases and Scenarios | CLOSED | CLOSED | CLOSED
135941 | Guideline | Achieving Concurrence | CLOSED | CLOSED | CLOSED
135941 | Checklist | Qualities of Good Requirements | CLOSED | CLOSED | CLOSED
135941 | Concept | Traceability | CLOSED | CLOSED | CLOSED
135941 | Concept | Requirements | CLOSED | CLOSED | CLOSED
135941 | Concept | Requirement Attributes | CLOSED | CLOSED | CLOSED
140073 | Artifact | Supporting Requirements | ASSIGNED | ASSIGNED | ASSIGNED
140073 | Template | Supporting Requirements | ASSIGNED | ASSIGNED | ASSIGNED
140073 | Guideline | Supporting Requirements | ASSIGNED | ASSIGNED | ASSIGNED
140073 | Checklist | Supporting Requirements | ASSIGNED | ASSIGNED | ASSIGNED
140073 | Concept | Supporting Requirements | ASSIGNED | ASSIGNED | ASSIGNED
140840 | Task | Define Vision | CLOSED | CLOSED | CLOSED
140844 | Task | Detail Requirements | CLOSED | CLOSED | CLOSED
140846 | Task | Find and Outline Requirements | CLOSED | CLOSED | CLOSED
140847 | Guideline | Achieving Concurrence | ASSIGNED | ASSIGNED | RESOLVED
140848 | Guideline | Find and Outline Actors and Use Cases | CLOSED | CLOSED | CLOSED
140850 | Guideline | Use Case Formats | NEW | ASSIGNED | RESOLVED
140852 | Guideline | Use Case Model | NEW | ASSIGNED | ASSIGNED
140856 | Checklist | Use Case Model | NEW | ASSIGNED | ASSIGNED
140858 | Checklist | Use Case | ASSIGNED | ASSIGNED | RESOLVED
140859 | Checklist | Vision | ASSIGNED | ASSIGNED | ASSIGNED
140865 | Concept | Use Case | RESOLVED | RESOLVED | RESOLVED
140867 | Checklist | Actor | NEW | ASSIGNED | RESOLVED
140871 | Artifact | ActorGoal List | CLOSED | CLOSED | CLOSED
141624 | Checklist | Qualities of Good Requirements | CLOSED | CLOSED | CLOSED
143741 | Concept | Requirements | CLOSED | CLOSED | CLOSED
143764 | Task | Find and Outline Requirements | RESOLVED | CLOSED | CLOSED
143764 | Task | Detail Requirements | RESOLVED | CLOSED | CLOSED
143764 | Task | Define Vision | RESOLVED | CLOSED | CLOSED
143764 | Artifact | Glossary | RESOLVED | CLOSED | CLOSED
143764 | Artifact | Use Case | RESOLVED | CLOSED | CLOSED
143764 | Artifact | Supporting Requirements | RESOLVED | CLOSED | CLOSED
143764 | Template | Supporting Requirements | RESOLVED | CLOSED | CLOSED
143764 | Template | Glossary | RESOLVED | CLOSED | CLOSED
143764 | Guideline | Use Case Formats | RESOLVED | CLOSED | CLOSED
143764 | Guideline | Achieving Concurrence | RESOLVED | CLOSED | CLOSED
143764 | Checklist | Use Case | RESOLVED | CLOSED | CLOSED
143764 | Checklist | Qualities of Good Requirements | RESOLVED | CLOSED | CLOSED
143764 | Concept | Use Case | RESOLVED | CLOSED | CLOSED
143764 | Concept | Supporting Requirements | RESOLVED | CLOSED | CLOSED
143764 | Concept | Requirements | RESOLVED | CLOSED | CLOSED
144235 | Guideline | Writing Good Requirements | CLOSED | RESOLVED | RESOLVED
145773 | Guideline | Detail Use Cases and Scenarios | ASSIGNED | ASSIGNED | RESOLVED
145775 | Artifact | Use Case Storyboard | NEW | NEW | NEW
147349 | Concept | Use Case Model | ASSIGNED | ASSIGNED | RESOLVED
147349 | Checklist | Use Case Model | ASSIGNED | ASSIGNED | RESOLVED
147349 | Guideline | Use Case Model | ASSIGNED | ASSIGNED | RESOLVED
147351 | Concept | Use Case Model | ASSIGNED | ASSIGNED | ASSIGNED
147354 | Artifact | Vision | NEW | NEW | NEW
147356 | Role | Analyst | NEW | NEW | NEW
147431 | Artifact | Actor | NEW | ASSIGNED | RESOLVED
147974 | CapabilityPattern | Manage Requirements |  | ASSIGNED | ASSIGNED
| Discipline | Overview
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 15 | 21 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 16 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 23 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burndown Work Area:
|  | Date | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 23 | 24 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Architecture
| Committer: | Mark Dickson, Xansa | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
143180 | Role | Architect | Assigned | Assigned | Assigned
143181 | Task | Define Architecture | Assigned | Assigned | Assigned
143182 | Task | Refine Architecture | Assigned | Assigned | Assigned
143183 | Task | Demonstrate Architecture | Assigned | Assigned | Assigned
| Work Product | Architecture
143184 | Work Product | Architectural Proof-of-Concept | Assigned | Assigned | Assigned
143187 | Concept | Component | New | New | New
143192 | Guideline | Layering | New | New | New
143189 | Concept | Patterns | Assigned | Assigned | Assigned
| Principle | Using Patterns
143190 | Checklist | Architecture | Assigned | Assigned | Assigned
| Capability Pattern | Define Architecture
| Capability Pattern | Determine Architectural Feasibility
| Discipline | Overview
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burndown Work Area:
|  | Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Development
| Committer: | Brian G. Lyons, Number Six Software, Inc. | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
145171 | Role | Developer | Assigned | Resolved | Resolved
146946 | Role | Developer (vm) | New | New | New
147148 | Task | Design the Solution | New | Assigned | Resolved
147152 | Task | Design the Solution (vm) | New | New | New
147161 | Task | Implement Developer Tests | New | New | New
147141 | Task | Implement Solution | New | New | Assigned
147171 | Task | Integrate and Create Build | New | New | New
147166 | Task | Prototype the User Interface | New | New | New
147162 | Task | Run Developer Tests | New | New | New
147149 | Work Product | Design | New | Assigned | Resolved
147153 | Work Product | Design (vm) | New | New | New
147172 | Work Product | Build | New | New | New
147163 | Work Product | Developer Test | New | New | New
147144 | Work Product | Implementation | New | New | Assigned
147154 | Work Product | Design Component | New | New | New
147155 | Work Product | Use-Case Realization | New | New | New
147167 | Work Product | UI Prototype | New | New | New
147176 | Concept | Refactoring | New | New | New
147165 | Concept | Test First Design | New | New | New
147177 | Concept | Continuous Integration | New | New | New
147151 | Checklist | Design | New | New | New
147150 | Guideline | Design | New | New | Resolved
147178 | Guideline | Continuous Integration | New | New | New
147147 | Guideline | Implementation | New | New | Assigned
147173 | Guideline | Promoting Builds | New | New | New
147174 | Guideline | Refactoring | New | New | New
147169 | Guideline | User-Interface Prototype | New | New | New
147164 | Guideline | Unit Test | New | New | New
147157 | Guideline | Design Components Representation | New | New | New
147158 | Guideline | Use-Case Realizations | New | New | New
147156 | Concept | Entity Control Boundary Pattern | New | New | New
| Capability Pattern | Develop Solution
| Discipline | Overview
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 30 | 28 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burndown Work Area:
|  | Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 31 | 30 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Test
| Committer: | Brian G. Lyons, Number Six Software | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
146501 | Role | Tester | Assigned | Assigned | Assigned
147182 | Task | Create Test Case | Assigned | Assigned | Assigned
146937 | Task | Evaluate Test Results | Assigned | Assigned | Assigned
147183 | Task | Implement Tests | Assigned | Assigned | Assigned
146940 | Task | Run Tests | Assigned | Assigned | Assigned
147184 | Work Product | Test Case | Assigned | Assigned | Assigned
147185 | Work Product | Test Data | Assigned | Assigned | Assigned
146938 | Work Product | Test Log | Assigned | Assigned | Assigned
146941 | Work Product | Test Script | Assigned | Assigned | Assigned
147194 | Concept | Test Ideas | Assigned | Assigned | Assigned
147188 | Concept | Types of Test | Assigned | Assigned | Assigned
147195 | Checklist | Test Script | Assigned | Assigned | Assigned
147186 | Checklist | Test Case | Assigned | Assigned | Assigned
147187 | Checklist | Test Data | Assigned | Assigned | Assigned
147189 | Guideline | Failure Analysis and Report Creation | Assigned | Assigned | Assigned
147196 | Guideline | Maintaining Automated Test Suite | Assigned | Assigned | Assigned
147198 | Guideline | Programming Automated Tests | Assigned | Assigned | Assigned
147191 | Guideline | Test Ideas | Assigned | Assigned | Assigned
147193 | Guideline | Test Suite | Assigned | Assigned | Assigned
| Capability Pattern | Test
| Discipline | Overview
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Change_Management
| Committer: | Chris Sibbald, Telelogic | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
134898 | MethodPackage | Change Management | CLOSED | CLOSED | CLOSED
136341 | Task | Request Change | CLOSED | CLOSED | CLOSED
136341 | Concept | Workspace | CLOSED | CLOSED | CLOSED
136341 | Guideline | Change Requests | CLOSED | CLOSED | CLOSED
136341 | Concept | Change Requests | CLOSED | CLOSED | CLOSED
147975 | CapabilityPattern | On-going Tasks |  | ASSIGNED | ASSIGNED
| Capability Pattern | Manage Changes
| Discipline | Overview
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Date | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Project_Management
| Committer: | Chris Armstrong, APG | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
| Role | Project Manager
| Task | Assess Results
| Task | Close Out Project
| Task | Initiate Iteration
| Task | Monitor and Control Project
| Task | Plan Iteration
| Task | Plan the Project
| Work Product | Iteration Plan
| Work Product | Project Plan
| Work Product | Status Assessment
| Work Product | Work Items List
146437 | Concept | Milestone | New | New | New
| Concept | Metrics
146441 | Concept | Risk | New | New | New
| Guideline | Assign Changes to Iteration
| Guideline | Assign Work
| Guideline | Estimation
| Guideline | Iteration Planning
| Guideline | Prioritizing Work
| Guideline | Project Plan
| Guideline | Risk List
| Guideline | Staffing Project
| Guideline | Status Assessment
| Guideline | Time Boxed Iterations
| Guideline | Type and Frequency of Assessments
146467 | Guideline | Types of Metrics | New | New | New
| Guideline | Work Items List
| Practice | Building Effective Teams
| Practice | Managing Risk
| Capability Pattern | Assess and Close Out Project
| Capability Pattern | Assess and Plan Iteration
| Capability Pattern | Initiate Project
| Capability Pattern | Manage Iteration
| Discipline | Overview
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## General
| Committer: | Steve Adolph, UBC | Status
Bug | Item Type | Name | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
| Role | Any Role
| Concept | Change Requests
| Concept | Prototype
| Concept | Stakeholder
| Supporting Material | Getting Started
| Supporting Material | Overview
| Supporting Material | References
| Guideline | Conduct Review/Concurrence
| Phase Iteration Template | Construction Phase Iteration
| Phase Iteration Template | Elaboration Phase Iteration
| Phase Iteration Template | Inception Phase Iteration
| Phase Iteration Template | Transition Phase Iteration
| View | Team
| View | Getting Started
| Work Product Kind | Assessment
| Work Product Kind | Concept
| Work Product Kind | Infrastructure
| Work Product Kind | Model
| Work Product Kind | Model Element
| Work Product Kind | Plan
| Work Product Kind | Project Data
| Work Product Kind | Solution
| Work Product Kind | Specification
|  | Unconfirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plan: Glidepath (to be changed only at iteration ends) | 23 | 24 | 18 | 15 | 12 | 9 | 6 | 3 | 0