## Sheet1
This worksheet provides status of the OpenUP/Basic content as of May 26 for all Guidance excluding Practices (which are different from a meta-model perspective) and elements in the base concepts package.
Status Legend:
| proposed | Not in current library, but may be a good idea
| included | Element included in library but not complete
| draft complete | Content exists but requires review
| reviewed | Review completed and comments available for action
| finalized | Review comments incorporated and final content (and relationships) accepted.
Number | Method Element | Type | Comment | Status | Related Bugzilla Entry
1 | Architecture | MethodPackage |  | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134897
1.1 | Visual Modeling | MethodPackage
1.1.1 | Visual Modeling | Concept | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143178
1.2 | Analysis Mechanisms | Concept | Content requires update. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143186 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143188
1.3 | Component | Concept | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143187
1.4 | Desing and Implementation Mechanisms | Concept | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143188 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143186
1.5 | Patterns | Concept | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143189
1.6 | Architecture | Checklist | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143190
1.7 | Create Architectural Proof of Concept | Guideline | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143191
1.8 | Layering | Guideline | draft content available | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143192
1.9 | Represent Interfaces to External Systems | Guideline | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143193
2 | Change Management | MethodPackage |  |  | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134898
2.1 | Change Requests | Concept |  | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=136341
2.2 | Change Requests | Guideline |  | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=136341
2.3 | Workspace | Concept |  | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=136341 https://bugs.eclipse.org/bugs/show_bug.cgi?id=138755
3 | Development | MethodPackage |  |  | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134899 https://bugs.eclipse.org/bugs/show_bug.cgi?id=138755 https://bugs.eclipse.org/bugs/show_bug.cgi?id=141692
3.1 | Visual Modeling | MethodPackage
3.1.1 | Analysis Classes | Concept | Proposal to remove and replace with Entity-Boundary-Controller pattern concept. | removed
3.1.2 | Design Components Representation | Guideline |  | included
3.1.3 | Finding Analysis Classes | Guideline | Proposal to remove (TBC) | included
3.1.4 | Use Case Realizations Representation | Guideline | Proposal to rename "Use Case Realization" and to describe how to apply the E-C-B pattern. | included
3.2 | Test First Design | Concept | Need content | included
3.3 | Design | Checklist | Need content | included
3.4 | Continuous Integration | Guideline | Need content | included
3.5 | Design | Guideline | Need content | included
3.6 | Implementation | Guideline | Need content | included
3.7 | Promoting Builds | Guideline | Need content. Should be consistent and reference Concept:Workspace | included
3.8 | UI Prototype | Guideline | Need content | included
3.9 | Unit Test | Guideline | Need content. To be renamed "Developer Test" | included
4 | General | MethodPackage |  | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134912
4.1 | Core Concepts | MethodPackage | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=132062 https://bugs.eclipse.org/bugs/show_bug.cgi?id=134912 https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.1 | Core Concepts | Concept | Significant changes expected. Currently working on these. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=133174 https://bugs.eclipse.org/bugs/show_bug.cgi?id=134912
4.1.2 | Architecture - Long Live Architecture | Concept | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138784
4.1.3 | Collaboration: It's the People! | Concept | Significant changes expected. Currently working on these. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=133174 https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.4 | Iteration - Do it again, and again.. | Concept | Significant changes expected. Currently working on these. Ricardo created draft content, not yet integrated into library. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138786
4.1.5 | Requirements Management - Know what they want | Concept | Significant changes expected. Currently working on these. Chris provided draft content, not yet integrated into libary. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138787
4.1.6 | Collaborative Practice Buddy Up | Guideline | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.7 | Collaborative Practice Confession is Good for the Soul | Guideline | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.8 | Collaborative Practice Continuous Learning | Guideline | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.9 | Collaborative Practice Manage by Intent | Guideline | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.10 | Collaborative Practice Share the Dream | Guideline | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.1.11 | Collaborative Practice Tear Down the Walls | Guideline | Significant changes expected. Currently working on these. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138781
4.2 | Introduction to OpenUP/Basic | Supporting Material |  | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138776
4.3 | References | Supporting Material |  | draft completed
4.4 | OpenUP/Basic Roadmap | Roadmap |  | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140019
5 | Project Management | MethodPackage | Kirti originally had ownership in accordance with associated bug, however this was passed to Chris Armstrong on May 16, 2006. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=132059 https://bugs.eclipse.org/bugs/show_bug.cgi?id=134914 https://bugs.eclipse.org/bugs/show_bug.cgi?id=136198 https://bugs.eclipse.org/bugs/show_bug.cgi?id=138753
5.1 | Iteration | Concept | There are two concepts called "Iteration" in the Browsing view. One in the OpenUP/Basic::Project Management package and one base concepts::General Guidance package. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=141596
5.2 | Metrics | Concept |  | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=138753
5.3 | Milestones | Concept | Content required | included
5.4 | Risk | Concept |  | draft completed
5.5 | Assign Changes to an Iteration | Guideline | Draft provided by Chris Sibbald as part of Change Management discipline and moved to PM discipline. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=136341
5.6 | Assigning Work | Guideline | Content required | included
5.7 | Estimation | Guideline |  | draft completed
5.8 | Iteration Planning | Guideline |  | draft completed
5.9 | Prioritizing Work | Guideline | Content required | included
5.1 | Plan Project Phases | Guideline | Content required | included
5.11 | Risk List | Guideline |  | draft completed
5.12 | Staffing Project | Guideline | Content required | included
5.13 | Status Assessment | Guideline |  | draft completed
5.14 | Time Boxed Iterations | Guideline | Content required | included
5.15 | Type and Frequency of Assessments | Guideline | Content required | included
5.16 | Types of Metrics | Guideline | Content required | included
5.17 | Work Item List | Guideline | Content required. Chris Armstrong to produce strawman. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135397 https://bugs.eclipse.org/bugs/show_bug.cgi?id=137120
6 | Requirements | MethodPackage |  | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134915
6.1 | Requirement Attributes | Concept | Complete. Proposal to delete (I don't agree). | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.2 | Requirements | Concept | Complete This concept should also be linked to Task:Define Vision and Task:Detail Requirements. See associate bug (enhancement). This has been implemented in bup_rm_plugin V0.4. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143741 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.3 | Supporting Requirements | Concept | Ana provided concept and I incorporated it in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.4 | Traceability | Concept | Complete. Proposal to delete (I don't agree). | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.5 | Use Case | Concept | Added content in bup_rm_plugin V0.4 based on RUP content. Linked to Guideline:Find and Outline Actors and Use Cases, Guideline: Detail Use Cases and Scenarios, Task:Detail Requirements, Task:Find and Outline Requirements, and Artifact:Use Case | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140865 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.6 | Use Case Model | Concept | Need concept (TBC). | proposed
6.7 | Actor | Checklist | Checklist exists. Needs content. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140867
6.8 | Qualities of Good Requirements | Checklist | Complete Checklist now associated with Artifacts Use Case, Vision and Supporting Requirements. Associations to Tasks: Find and Outline Requirements and Detail Requirements Removed. This was done in bup_rm_plugin V0.4. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=141624 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.9 | Supporting Requirements | Checklist | Feel it is not needed. Checklist Qualities of Good Requirements is associated with Artifact:Supporting Requirements in bup_rm_plugin V0.4 | proposed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073
6.1 | Use Case Model | Checklist | Needs Content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140856
6.11 | Use Case | Checklist | Content provided in bup_rm_plugin V0.4. (worked with Paul Bramble). | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140858 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.12 | Vision | Checklist | Checklist exists, need content. | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140859
6.13 | Achieving Concurrence | Guideline | Added this guideline to the guidance for Task: Find and Outline Requirements and Task: Detail Requirements in bup_rm_plugin V0.4. Guideline still needs to be re-written. Focus on requirement reviews only vs. general reviews. Re-use TwoTierReview from Paul? Should there be two guidelines: Review Use Cases, and Review Supporting Requirements? | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=140847 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.14 | Define Vision | Guideline | Should there be a guildeline for the Task:Define Vision similar to those for the other tasks? Or is Guideline: Requirements Gathering, Guideline:Achieve Concurrence and Checklist:Vision sufficient? | proposed
6.15 | Detail Use Cases and Scenarios | Guideline | Content available based on work with Paul Bramble. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.16 | Find and Outline Actors and Use Cases | Guideline | Complete based on work with Paul Bramble. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=140848
6.17 | Requirement Gathering Techniques | Guideline | Complete | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.18 | Requirement Pitfalls | Guideline | Complete | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.19 | Supporting Requirements | Guideline | Guideline exist (name and description only), is it needed or is Writing Good Requirements sufficient? | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941 https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073
6.2 | Use Case Formats | Guideline | Guidance on formality and format of use cases. Associate with Task:Detail Requirements and Template: Use Case Specification. May require update to Template:Use Case Specification. Added Guideline in bup_rm_plugin V0.4 including draft content from Paul. Added Guideline:Detail Use Case and Scenarios and Guideline:Use Case Formats to the Representation Options and associated guidance of Artifact:Use Case. Linked to Concept:Use Case. Need to Link to Template:Use Case Specification, Artifact: Use Case and Task:Detail Requirements. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140850 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.21 | Use Case Model | Guideline | Need Content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140852
6.22 | Use Case | Guideline | No longer in OpenUP (05/05/06). Replaced with Concept Use Case. Not sure if this is correct, perhaps guideline is the appropriate element. This element is linked to two instances of Artifact::Use Case. One in basic_unified_process plug-in and one in bup_rm plug-in. | removed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.23 | Writing Good Requirements | Guideline | Complete. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.24 | Requirement | Term Definition | Complete. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
7 | Templates | MethodPackage |  | included
7.1 | ActorGoal List | Template |  | proposed
7.2 | Glossary | Template | included in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134895 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
7.3 | Iteration Plan | Template |  | draft completed
7.4 | Project Plan | Template |  | draft completed
7.5 | Software Architecture Document | Template |  | draft completed
7.6 | Supporting Requirements | Template | included in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
7.7 | Test Case | Template |  | draft completed
7.8 | Use Case Specification | Template | Complete | draft completed
7.9 | Vision | Template | Complete | draft completed
8 | Test | MethodPackage |  |  | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134916
8.1 | Test Ideas | Concept | need content | included
8.2 | Types of Test | Concept | need content | included
8.3 | Test Case | Checklist | need content | included
8.4 | Test Script | Checklist | need content | included
8.5 | Failure Analysis Report Creation | Guideline | need content Should be associated with Task:Submit Change | included
8.6 | Maintaining Automated Test Suite | Guideline | needs content | included
8.7 | Programming Automated Tests | Guideline | needs content | included
8.8 | Test Case | Guideline | needs content Should be associated with task create test case as well. | included
8.9 | Test Data | Guideline | needs content Should be associated with task create test case and task implement test as well. | included
8.1 | Test Ideas | Guideline | needs content | included
8.11 | Test Suite | Guideline | needs content | included