## Sheet1
This worksheet provides status of the OpenUP/Basic content as of May 26 for all work products
Status Legend:
| proposed | Not in current library, but may be a good idea
| included | Element included in library but not complete
| draft complete | Content exists but requires review
| reviewed | Review completed and comments available for action
| finalized | Review comments incorporated and final content (and relationships) accepted.
Number | Method Element | Type | Comments | Status | Related Bugzilla Entry
1 | Architecture | MethodPackage
1.1 | Architecture Proof-of-Concept | Artifact | Do we really need this as a distinct artifact. I would think that there is only one artifact: Architecture that is evolved, not two distinct Architectures? | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143184
1.2 | Architecture | Artifact | Needs content | included | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143185
2 | Change Management | MethodPackage
3 | Development | MethodPackage
3.1 | Visual Modeling | MethodPackage
3.1.1 | Design Component | Artifact | Needs content | included
3.1.2 | Use Case Realization | Artifact | Need content | included
3.2 | Build | Artifact | Needs content | included
3.3 | Design | Artifact | Need content | included
3.4 | Developer Test | Artifact | Need content | included
3.5 | Implementation | Artifact | Needs content | included
3.6 | UI Prototype | Artifact | Needs content | included
4 | General | MethodPackage
5 | Project Management | MethodPackage
5.1 | Iteration Plan | Artifact |  | draft completed
5.2 | Project Plan | Artifact |  | draft completed
5.3 | Status Assessment | Artifact |  | draft completed
5.4 | Work Items List | Artifact | Work on WIL still on-going. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=137120
6 | Requirements | MethodPackage
6.1 | ActorGoal List | Artifact | If we make UC Model optional there should be an artifact that captures Actors. | proposed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140871
6.2 | Glossary | Artifact | updated in bup_rm_plugin V0.4 | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=134895 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.3 | Supporting Requirements | Artifact | Incorporated in bup_rm_plugin v0.4. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=140073 https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.4 | Use Case Model | Artifact | Exists. Proposal to make this optional and factor out into another package. | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=135941
6.4.1 | Use Case | Artifact | Complete | draft completed | https://bugs.eclipse.org/bugs/show_bug.cgi?id=143764
6.4.2 | Actor | Artifact | Exists, but only captured in UC Model. If we make UC Model optional we will need an Actor list. This WP does not show up as the input or output of any task because only the Use-Case model is an input or output. If we wish to make UC Model optional we will have to update OpenUP to list UC as input/output as appropriate. | draft completed
6.5 | Vision | Artifact | needs content | included
7 | Templates | MethodPackage
8 | Test | MethodPackage
8.1 | Test Case | Artifact | Needs content | included
8.2 | Test Data | Artifact | Needs content | included
8.3 | Test Log | Artifact | Needs content No guidance associated with this artifact | included
8.4 | Test Script | Artifact | Needs content | included