## Slide 1
Goofy's strawman plan*
and dev process proposal
Jasmine's lessons learned
summit
* https://www.linkedin.com/pulse/strawman-project-plan-what-why-should-you-use-one-brian-fredrickson

## Slide 2
RETROSPECTION

## Slide 3: Jasmine’s development plan
Designing the roadmap
Requirements gathering
HW Roadmap definition
Requirements acceptance
Requirements decomposition and workload estimation
Team capacity planning
Plan execution with ongoing plan vs execution verification
Periodical requirements backlog update
😐

## Slide 4: Release schedule
Release Schedule
22 Feb – Aladdin Features Freeze
2 Apr – Go/No-go
12 Apr – Aladdin General Availability 22 Jun – Jasmine Alpha
14 Sep – Jasmine Beta
22 Nov – Jasmine Release Candidate
?? Dec – Go/No-go
20 Dec – Jasmine General Availability
1st official Oniro LTS release
*Quarterly realease cycle
😀

## Slide 5: Jasmine’s scrum
Sprints schedule
Sprint 1 (21 Apr - 11 May)
Sprint 2 (12 May - 01 Jun)
Sprint 3 (02 Jun - 22 Jun)
Sprint 4 (23 Jun - 13 Jul)
Sprint 5 (14 Jul - 03 Aug)
Sprint 6 (04 Aug - 24 Aug)
Sprint 7 (25 Aug - 14 Sep)
Sprint 8 (15 Sep - 05 Oct)
Sprint 9 (06 Oct - 28 Oct)
Sprint 10 (29 Oct - 16 Nov)
*3 weeks cycle
🙁

## Slide 6: Jasmine’s scrum meetings
Weekly Update - every Thursday, 10 - 11 AM CET
Sprint Review - every 3rd Tuesday, 2 - 3 PM CET
Sprint Retrospective - every 3d Wednesday, 12 - 1 PM CET
Sprint Planning - every 3rd Friday, 10 - 11 AM CET
😀

## Slide 7: Sprint planning vs execution
Misalignment between planning and execution
Overoptimistic planning
Underestimated side activities
New and growing team
To big chunks of works too hard to estimate
Reasearch type of work
🙁

## Slide 8: Performance monitoring
Lack of automated performance monitoring
🙁

## Slide 9: Requirements management
Selection:
  Acceptance of requirements set for release
  Ongoing requirements backlog filling
  Periodical requirements backlog review and release backlog update
OpenProject and then GitLab as a system of choice
May be proposed by any but must be agreed by all partners
Ambiguous closing criteria
Execution spanning multiple sprints and even releases
😐

## Slide 10: Systems we’ve used
OSTC GitLab - code, tasks management, planning, documents storage
Booting GitLab - code, tasks management, planning, documents storage
OSTC Mattermost - chat
Booting Mattermost- still booting
OSTC Discourse - forum
OSTC OpenProject - requirements management (deprecated)
IRC - IRC public chat
🙁

## Slide 11: Planning, monitoring, reporting
Tasks managed in GitLab
Requirements managed in OpenProject, moved to GitLab lately
Planning and review meetings every sprint cycle
Weekly engineering syncup meetings documented in GitLab
Weekly report sent by project manager to all parties on Friday
Periodical requirements review meeting
😀
https://git.ostc-eu.org/OSTC/planning/scrum/-/blob/master/WGEngineeringWeeklyReports/README.md
https://git.ostc-eu.org/OSTC/planning/scrum/-/wikis/home
https://git.ostc-eu.org/groups/OSTC/-/boards/100?iteration_id=Current
https://project.ostc-eu.org/projects/open-source-technology-center-eu/
https://git.ostc-eu.org/OSTC/requirements/-/issues

## Slide 12
WHAT NOW?

## Slide 13: Designing the roadmap
Goofy roadmap design should follow Jasmin best practices
  Requirements gathering (ongoing)
  Final release scope definition (end of Feb 2022)
  Workload estimation done by whole engineering team (change)
  Manpower and cost estimation (time is bounded, quality defined by requirements)
  Release scope reevaluation (if necessary)
  Project execution
  Ongoing requirements review
😀
What kind of manpower we can expect for Goofy?

## Slide 14: Release cycle for Oniro 2.0 LTS (Goofy)
52 weeks total = 1 year
Longer sprints to minimize related overhead
Release every quarter
Stabilization phase with intense testing before GA
Planning considered in schedule
😀

## Slide 15: Scrum updated
  4 weeks cycle
  Effort planning
    Moving from hours to points (??)
    Better control over under/over planning to improve predictability (supported by automated tools)
    Done by allocated sub-groups divided by technological areas
  Maintained periodical meetings (planning, closing, retro, weekly)
😀
Rotational Project Management
Who will drive Goofy?

## Slide 16: Requirements management improvements
Requirements should:
clearly define benefits
indicate beneficent(-s)
have accountable person(-s) assigned
span for no more than 2 sprints
have clear testing and closing criteria
be automatically linked with tasks (same system preferred)
😀
Lack of test team
How to staff test team before Goofy starts?

## Slide 17: Other improvements
Define and follow QA process
Automate data gathering including project metrics
Minimize number of systems used
Common videoconferencing system for whole WG
😀

## Slide 18: JOIN ONIRO PROJECT
Thank you!
Join us on oniroproject.org

## Slide 19: PRODUCT RELEASE LIFECYCLE
* https://git.ostc-eu.org/OSTC/planning/maintenance/-/wikis/Releases-and-supportability

## Slide 20: HARDWARE ENABLEMENT ROADMAP
Heterogeneous Communication Infrastructure
Yocto Project
Compatible
OpenChain
Compilance
Devices Ontologies
Doorlock
Trasparent Gateway
Zephyr Compatibility
Touch Control Panel
LAVA based Device Testing Infrastucture
Resource Discovery and Directory
Openharmony
Compatibility
Linux 5.10 LTS
Zephyr 2.4 LTS
Reference
Hardware
Runtime and
Tools
Q1
Q2
Q3
Q4
Autonomous
Agency
Reference
Blueprints
Testing &
Infrastructure
Standards &
Compliance
96Boards Nitrogen Zephyr
96Boards Avenger Zephyr and Linux
QEMU ARM and Intel Zephyr and Linux
Secure Boot
App SDK, App Runtime,
Linux Graphics
OpenHarmony Compatibility Kit
Device Testing Blueprint
Vending Machine
Seco SBC B68 Linux
Raspberry PI4 Linux
Seco SBC C61 Zephyr and Linux
Arduino Nano 33 BLE Zephyr
Zephyr 2.6 LTS
LiteOS 21.1 LTS
Security kernel and toolchain
MQTT
Open Thread
Secure System OTA
COAP
CHIP
(Linux and Zephyr)

## Slide 21: LIFECYCLE AND RELEASE SCHEDULE
YEAR 1
All
All
All Toolchain CVSS 9-10
YEAR 2
YEAR 3
BUGS
CVEs
1.0 JASMINE RELEASE
TOOLCHAIN UPGRADE
2.0 GOOFY RELEASE
3.0 DAISY RELEASE
2020
2022
2024
2021
2023
2025
2026
LTS y.1
LTS y.3
Development
LTS y.1
LTS y.3
LTS y.2
Development
P1/P2
CVSS 7-10
Toolchain CVSS 9-10
P1
KERNEL UPGRADE
USER SPEC UPGRADE
(2021)
(2022)
(2023)
Development
LTS y.1
LTS y.2
LTS y.3
LTS y.2
BSPS UPGRADE/OBSOLENCE

## Slide 22: DEVELOPMENT TOOLS: COMPILERS, DEBUGGERS, IDE,...
SUPPORTED
ARCHITECTURE
SUPPORTED
KERNEL
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
Jasmine
2021
2021
2021
2021
2021
2021
2021
2021
2021
2021
2021
2021
2021
11.1
12.0.1
2.37
9.1
5.10.x
5.10.x
5.5
244.5
5.10.x
*
TBD
ARM, Intel, RISC-V
ARM, Intel, RISC-V
ARM, Intel, RISC-V
ARM, Intel
ARM, Intel
ARM, Intel
ARM, Intel
ARM, Intel
ARM, Intel
ARM, Intel
ARM, Intel
Linux, Zephyr,
Liteos, FreeRTOS
Linux, Zephyr,
Liteos, FreeRTOS
Linux, Zephyr,
Liteos, FreeRTOS
Linux, Zephyr,
Liteos, FreeRTOS
Linux
Linux
Linux
Linux
Linux, Zephyr,
Liteos, FreeRTOS
Linux
Kernel and app developer
Kernel and app developer
Kernel and app developer
App developer
Kernel and HW developer
Kernel and HW developer
Kernel and app developer
Kernel developer
Kernel/System developer
Kernel developer
App developer
App developer
Fronted developer
Toolchain
Toolchain
Toolchain
debugger
debugger
debugger
syscall tracing
memory profiling
boot time analysis
cpu load profiling
application sdk
java sdk
GCC
LLVM
binutils
gdb
kgdb over ethernet
kgdb over serials
strace
TBD-heaptrack?
Systemd-analyze
perf
sysroot
openjdk
<add>
TOOL
TYPE
VERSION
TARGET PERSONAS
TARGET RELEASE
YEAR OF RELEASE