| Work Item | Responsibility | Critical Success Factor | Target Date | Status |
| --- | --- | --- | --- | --- |
| Legal Issues |  |  |  |  |
| Review Terms of Use & Privacy Policy | Temp Closed |  |  | Deferred to later discussion. |
| Policy Items |  |  |  | Mike T to lead working group with Donald/Ian regarding items |
| Google Advertising | Mike T / Skip |  | Aug 1 | To be readdressed on Aug 1. Working group to look at options for posting ads and earning revenue to fund advertisng. |
| Public Ranking | Eric/Maher/Ian/Nathan |  |  |  |
| Advertising | Ian |  | Q3 – Aug 15 | Banner ads on popular sites to link to EPIC. Ian to work with Mike T and Maher on ads. Ads to start between Aug 15/Sept 1. |
| Publish Guidelines |  |  |  |  |
| Develop and publish a set of design guidelines and principles that will define the look and feel, navigation and UI of EPIC | Nathan |  | Q4 | Nathan to include Maher and Susan Iwai on feedback. |
| Develop and publish a set of content and participation guidelines that will 1) define the principles and processes of publishing content, 2) provide openness to all individuals and organizations and 3) define a set of principles for providing preferential visibility and capabilities to Members | Nathan Ian Maher | YES | Q3 – July 25 | Goal is to publish guidelines to main EPIC site. Solicit community feedback. Draft sent July 17, team should review for July 25. |
| Communication |  |  |  |  |
| Communication plan including media/mindshare actions. | Ian, Mike T |  |  |  |
| Communication integration between EPIC and the rest of www.eclipse.org Special emphasis on plugin catalog, news, membership information | Nathan Donald |  | Q3 | Plug in catalog |
| Governance |  |  |  |  |
| Council Governance Review | Skip, Maher, Mike |  | To be closed August 15 | Skip to lead review of governance documents to work on plan for completing the Governance work items below. |
| Selection of Council Leaders | Closed |  |  | See “Council Governance Review” |
| Process for minutes and transparency | Donald |  | July 25 | Don to place process on WIKI. Will note that HR and Privacy issues will not be posted as well. |
| Develop and monitor the plan to follow the open source paradigm | On hold |  |  | See “Council Governance Review” |
| Disclosure of public parts of governance Doc | Eric/Skip |  | Closed. | Eric to post on Wiki the appendix part of governance document + any additional information needed |
| Operations |  |  |  |  |
| Define the process for creation, review and approval by the council of the quarterly operational plan that includes: Tasks to be completed that Dependencies Top Requirements not met Deliverables Schedules Significant changes to plan Solicit community feedback New Application directions | Nathan Skip |  |  |  |
| Develop and communicate the operations plan and management structure to the council. This is to include roles, responsibilities funding | Skip |  |  |  |
| Articulate (write proposed text) the EPIC Vision | Mike Ian | Yes | CLOSED | Post on Wiki plus add to “about page”on EPIC |
| Establish 8 to 9 Add-In Provider early adopters | Howard |  | CLOSED | Moved to Member Outreach and Participation Program |
| Develop requirements themes and prty | Ian Nathan Howard Eric | Yes |  | Ongoing |
| Develop and articulate the value propositions for EPIC and communicate it via the communication plan | Ian Mike T |  | CLOSED. |  |
| Member Outreach and Participation Program | Eric/Skip/Mike/Howard Skip |  |  | Visability of Eclipse Projects “Reach out to projects” Include and interact with OS Projects on EPIC? New KPI – Member participation % on EPIC |
| Member Survey | Eric/Skip/Mike/Donald |  | Q3 | Survey – Skip to circulate questions to working group. |
| Development Plan |  |  |  |  |
| Short term plan to make changes which are necessary to current site | Nathan | YES | Q3 |  |
| Develop capacity plan | Nathan | YES | Q3 | Nathan to work with Denis, this is more about understanding the eclipse.org infrastructure plan |
| Develop process for participation | Nathan | YES | Q3 |  |