## bugs-2008-05-12
bug_id | changeddate | bug_severity | priority | assigned_to | bug_status | component | version | target_milestone | short_short_desc
231520 | 2008-05-12 06:59 | blocker | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3M2 | Can't deploy plugin | Yes
221406 | 2008-04-24 13:08 | critical | P3 | tigerstripe.diagram-inbox@eclipse.org | ASSIGNED | Diagrams | unspecified | 0.3M2 | When diagrams are in Error (missing either GMF file) an Error should be raised in the problems view | Yes
222705 | 2008-04-24 13:10 | major | P3 | erdillon@cisco.com | NEW | Core | unspecified | 0.3M2 | Moving Self Association Class hangs Tigerstripe | Yes
214509 | 2008-01-07 11:03 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | --- | Subclipse change tags on diagrams is not correct
217970 | 2008-02-19 15:18 | normal | P3 | rcraddoc@cisco.com | NEW | Core | unspecified | S0.2.2.5 | No checking of type of a Literal in API
219034 | 2008-02-28 12:07 | normal | P3 | erdillon@cisco.com | NEW | Core | unspecified | S0.2.2.5 | Tigerstripe's metamodel should leverage EMF
219412 | 2008-02-19 05:22 | normal | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | S0.2.2.5 | Enum wizard is inconsistent
219565 | 2008-02-20 03:36 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | S0.2.2.5 | Auditor reports invalid diagram error
219575 | 2008-02-20 05:38 | normal | P2 | tigerstripe.core-inbox@eclipse.org | NEW | Core | unspecified | S0.2.2.5 | Disabling artifacts in profile has variable impact
220345 | 2008-05-07 19:16 | normal | P3 | erdillon@cisco.com | NEW | Core | unspecified | S0.2.2.5 | New MetaModel Issues
220536 | 2008-02-27 05:08 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | S0.2.2.5 | Reference links are not managed in the same way as associations
220933 | 2008-03-04 21:47 | normal | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | S0.2.2.5 | Need better warning when cascade delete is used.
221435 | 2008-03-04 21:00 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | S0.2.2.5 | Default Diagram Box size is a bit too small
221441 | 2008-03-06 00:57 | normal | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | S0.2.2.5 | Extend 'Manage Links ...' functionality to all Relationships
221442 | 2008-04-02 21:06 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | S0.2.2.5 | Copy attribute on diagram using <ctrl> drag & drop
221444 | 2008-03-04 22:21 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | S0.2.2.5 | Improve Association creation on diagram
221452 | 2008-05-02 04:40 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | unspecified | S0.2.2.5 | TS 2.2.4.N Performance Issues
222720 | 2008-04-24 13:21 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | unspecified | 0.3M1 | Rename IArtifactModel
230101 | 2008-05-04 03:35 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3M1 | Enhencement request: ordered associations in instance diagram
230367 | 2008-05-06 07:25 | normal | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | 0.3S4 | 0.3M1 | Enum base type is considered as an OSS/J specific
230368 | 2008-05-06 07:30 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3M1 | SetBaseType of EnumArtifact doesn't get saved ?
230376 | 2008-05-06 07:54 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3M1 | Auditor checking for OSS/J Specifics when they are disabled
227697 | 2008-04-24 13:47 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3M2 | Rename Interface not updating Entity Implements
228327 | 2008-04-24 13:48 | normal | P3 | rcraddoc@cisco.com | NEW | UI | 0.3S4 | 0.3M2 | Enum form not sorting in int order
229159 | 2008-05-05 13:51 | normal | P3 | jistrawn@cisco.com | NEW | Plugin | 0.3M0 | 0.3M2 | Tigerstripe Maven Plugin points to wrong executable when not running from Windows
230849 | 2008-05-07 13:09 | normal | P3 | erdillon@cisco.com | NEW | Annotations | 0.3M1 | 0.3M2 | Selection events for method parameters (and for methods themselves) in Tigerstripe artifact editor passed to annotations f/work with empty ISelection
230877 | 2008-05-07 13:11 | normal | P3 | jworrell@cisco.com | NEW | Annotations | 0.3M1 | 0.3M2 | No refactoring support for Togerstripe annotations
230930 | 2008-05-08 15:09 | normal | P3 | yuri@xored.com | NEW | Annotations | 0.3M1 | 0.3M2 | Annotation Property View editor fails for multi-valued references
230942 | 2008-05-07 13:32 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3M1 | 0.3M2 | ITigerstripeProfile should implement IWorkingCopy
230943 | 2008-05-07 13:33 | normal | P3 | tigerstripe.facet-inbox@eclipse.org | NEW | Facet | 0.3M1 | 0.3M2 | Facet should follow the IWorkingCopy patterns
231441 | 2008-05-10 13:53 | normal | P3 | yuri@xored.com | NEW | Annotations | 0.3M2 | 0.3M2 | Do not display classname/hashcode in the Annotation Property View
231444 | 2008-05-10 13:59 | normal | P3 | yuri@xored.com | NEW | Annotations | 0.3M2 | 0.3M2 | Remove annotation URI from the user
222502 | 2008-03-12 20:56 | normal | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | 0.3S2 | Annotation selection dialog box fixes
222611 | 2008-03-13 13:08 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S1 | 0.3S2 | Get error during package/deploy of plugin.
223047 | 2008-03-18 03:19 | normal | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | 0.3S3 | Stereotype not showing up in explorer
223400 | 2008-03-20 15:59 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3S3 | Hyperlink between diagrams
223440 | 2008-03-31 13:44 | normal | P3 | tigerstripe.facet-inbox@eclipse.org | NEW | Facet | 0.3S2b | 0.3S3 | Changes to model within active facet are not taken into account in facet
225520 | 2008-04-03 10:51 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | unspecified | 0.3S4 | No way to document operation return code/object
226387 | 2008-04-09 18:25 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S4 | 0.3S4 | Additional req. for Audit/Sync diagrams
226856 | 2008-04-13 22:13 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S4 | 0.3S4 | Default Line colour and undo don't restore correctly
227158 | 2008-04-24 13:46 | normal | P3 | tigerstripe.documentation-inbox@eclipse.org | NEW | Documentation | 0.3S4 | 0.3S4 | PlugIn Help is no longer helpful
228519 | 2008-04-23 16:42 | normal | P3 | tigerstripe.documentation-inbox@eclipse.org | NEW | Documentation | 0.3M0 | 0.3S4 | Review Tigerstripe branding
228696 | 2008-04-24 11:40 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3S4 | Define Extension points for audit checks
228699 | 2008-04-24 11:42 | normal | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3S4 | Define Extension points for new element naming
221468 | 2008-03-26 16:27 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | ASSIGNED | Diagrams | unspecified | S0.2.2.5 | Diagram audit - internal pointer file names
221432 | 2008-05-12 09:42 | normal | P3 | jistrawn@cisco.com | ASSIGNED | Core | 0.3S2 | 0.3M2 | isOrdered and isUnique disabled when upper cardinality <=1
230916 | 2008-05-12 01:19 | normal | P3 | yuri@xored.com | ASSIGNED | Annotations | 0.3M1 | 0.3M2 | Customize-able UI properties for Annotations
222771 | 2008-05-07 04:30 | normal | P3 | jworrell@cisco.com | ASSIGNED | Annotations | 0.3S1 | 0.3S2 | .annotation directories are added to all projects regardless.
219729 | 2008-04-17 00:45 | normal | P3 | rcraddoc@cisco.com | REOPENED | Diagrams | unspecified | 0.3S1 | Tigerstripe adds suffices to associaion ends unnecessarily
221453 | 2008-03-28 00:24 | normal | P3 | tigerstripe.diagram-inbox@eclipse.org | REOPENED | Diagrams | unspecified | 0.3S1 | Provide capability to copy diagrams (class and object)
216139 | 2008-01-22 08:34 | minor | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | unspecified | S0.2.2.5 | isValidAttribute method allows an invalid Attrbute to pass
219457 | 2008-02-22 09:13 | minor | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | S0.2.2.5 | Diagram audit confusing messages
231339 | 2008-05-09 13:08 | minor | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3M1 | 0.3M2 | Configuring velocity run time logger location and logger system class
225729 | 2008-04-04 08:17 | minor | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3S4 | Stereotypes of the same name in different profiles get deleted
226276 | 2008-04-23 08:08 | minor | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S1 | 0.3S4 | Add Referenced artifacts not disabled when references disabled in profile
226281 | 2008-04-09 09:36 | minor | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | 0.3S4 | 0.3S4 | Icons missing in Export wizard
228299 | 2008-04-22 18:37 | minor | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | 0.3S4 | 0.3S4 | Some editors do not close upon deployment of a profile.
225505 | 2008-04-22 18:13 | minor | P3 | jistrawn@cisco.com | ASSIGNED | UI | 0.3S4 | 0.3S4 | Annotation comment doesn't wrap in editor
230927 | 2008-05-07 12:35 | enhancement | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3M1 | --- | "Base" plugin should not be installed as "unjar" to avoid lengthy paths on windows.
217421 | 2008-02-01 05:18 | enhancement | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | unspecified | S0.2.2.5 | "Recover" profile from active session
221108 | 2008-03-03 03:27 | enhancement | P3 | tigerstripe.plugin-inbox@eclipse.org | NEW | Plugin | unspecified | S0.2.2.5 | Add a new rule type
221169 | 2008-03-03 17:10 | enhancement | P3 | tigerstripe.documentation-inbox@eclipse.org | NEW | Documentation | unspecified | S0.2.2.5 | Can't find any documentation.
221443 | 2008-03-05 13:39 | enhancement | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | S0.2.2.5 | Refactor Association <-> Association Class
221560 | 2008-03-05 12:26 | enhancement | P3 | tigerstripe.documentation-inbox@eclipse.org | NEW | Documentation | unspecified | S0.2.2.5 | Provide XSDs for XML config files - tigerstripe.xml etc.
230177 | 2008-05-05 07:01 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3M1 | Class diagram: Visualize an assciation between superclasses
230810 | 2008-05-07 01:30 | enhancement | P3 | erdillon@cisco.com | NEW | Plugin | 0.3M0 | 0.3M2 | Dumping classpath of a generation plugin into log file
222171 | 2008-03-11 02:58 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3S2 | Provide link name hiding options on instance diagrams
222173 | 2008-04-24 13:59 | enhancement | P3 | erdillon@cisco.com | NEW | UI | unspecified | 0.3S2 | Colour Icons for Artefact Types
222174 | 2008-03-11 03:17 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3S2 | Provide Suitable Fill Colours
222176 | 2008-03-11 03:33 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3S2 | Allow instance diagram link direction to be chosen
222500 | 2008-03-12 20:23 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | unspecified | 0.3S2 | Allow action bar to be disabled.
222533 | 2008-03-13 05:33 | enhancement | P3 | tigerstripe.ui-inbox@eclipse.org | NEW | UI | unspecified | 0.3S2 | Allow filtering of the Explorer view
226404 | 2008-04-09 22:07 | enhancement | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3S4 | 0.3S4 | Auto-tag new artefacts with stereotype on creation
226405 | 2008-04-09 22:14 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S4 | 0.3S4 | Provide 'Synch up with model' option for instance diagrams
226857 | 2008-04-13 22:20 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S4 | 0.3S4 | Provide diagram UML selection options
226978 | 2008-04-14 13:36 | enhancement | P3 | tigerstripe.plugin-inbox@eclipse.org | NEW | Plugin | 0.3S4 | 0.3S4 | Stderr and Stdout should be "capturable" during generation plugin runs.
227089 | 2008-04-15 04:47 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S4 | 0.3S4 | Provide Instance Diagram 'Add Related Artifact'
227246 | 2008-04-15 21:09 | enhancement | P3 | tigerstripe.diagram-inbox@eclipse.org | NEW | Diagrams | 0.3S4 | 0.3S4 | Provide enhanced diagram package display
228183 | 2008-04-22 07:27 | enhancement | P3 | yuri.strot@xored.com | NEW | Annotations | unspecified | 0.3S4 | Please remove dependency to EMF validation from annotations core
228545 | 2008-04-23 18:34 | enhancement | P3 | tigerstripe.core-inbox@eclipse.org | NEW | Core | 0.3M0 | 0.3S4 | Multiple XML parsers are used
228548 | 2008-04-23 18:58 | enhancement | P3 | tigerstripe.plugin-inbox@eclipse.org | NEW | Plugin | 0.3M0 | 0.3S4 | Create section on website for download-able plugins
221309 | 2008-03-04 15:04 | enhancement | P2 | erdillon@cisco.com | ASSIGNED | Diagrams | unspecified | S0.2.2.5 | Audit Instance diagram support
228670 | 2008-05-07 11:37 | enhancement | P3 | dkeysell@cisco.com | ASSIGNED | Documentation | 0.3M0 | 0.3M2 | TS should provide a way to generate documentation about models